## README
README - Governed Multi-Brand Agentic System Project Workbook
Project Window: Friday, September 11, 2026 through Wednesday, October 14, 2026 (34 calendar days)
Source of Truth: Project_Plan_Essentials-Governed_Multi-Brand_Agentic_System.md + Final-Level_Full_Architecture.md
1. Where to update tasks:
- Go to Tracker sheet. Editable columns are highlighted in light yellow: Start Date, End Date, Predecessor, Dependency Type, Resource/Owner, Status, Progress %, Milestone YES/NO, Milestone ID, Priority, Notes.
- Duration, Conflict/Validation, Current State, Latest Pred End are calculated (light blue) and update automatically.
- All dates use YYYY-MM-DD format. Duration = End-Start+1 inclusive calendar days.
2. How to change dates and dependencies:
- Edit Start Date / End Date directly in Tracker (cols E,F). Gantt bars recalculate via formulas =IF(AND(date>=Start,date<=End),...)
- Predecessor format: comma-separated Task IDs e.g. 'T01, T02' or 'None'. Use exact IDs from column A.
- Latest Predecessor End (col S) = MAX(XLOOKUP(TEXTSPLIT(Predecessor),TaskID,EndDate)). Conflict column Q flags '⚠ Pred conflict' if Start <= Latest Pred End.
- Dependency Type defaults to FS (Finish-to-Start) per architecture spec. Editable via dropdown FS/SS/FF/SF.
- Tasks outside project window 2026-09-11 to 2026-10-14 are flagged in Conflict column.
3. How to update Progress % and Status:
- Progress % (col L) accepts 0% to 100% (0 to 1 decimal). Data validation enforces 0-1 range.
- Status dropdown: Not Started, In Progress, Completed, On Hold, Delayed (Lists!A2:A6). Status should align with Progress: 0%=Not Started, 100%=Completed, but editable.
- Gantt visualization: Progress done portion = green (value 1), remaining = light blue (value 2). If Progress=100%, entire bar dark green (value 4).
- Milestone marker: Gold cell (value 3) at End Date when Milestone=YES. Milestone tasks: T03,T04,T10,T14,T20,T21,T24,T29,T34.
- Current State (col R) auto-calculates based on Report Date (Dashboard!B2) and Progress: Completed / Active / Overdue / Upcoming / At Risk.
4. How the Gantt visualization updates:
- Gantt sheet pulls Task ID, Phase, Task Name, Resource, Status, Progress, Start, End, Milestone flag from Tracker via =Tracker! formulas (cols A-I).
- Date headers J2:AR2 = each calendar day Sep 11-Oct 14. Row 3 = weekday, Row 4 = MM/DD. Weekend columns highlighted via conditional formatting WEEKDAY>=6.
- Each Gantt cell formula: =IF(AND(date>=Start,date<=End),IF(AND(Milestone=YES,date=End),3,IF(Progress=1,4,IF(date<=Start+Duration*Progress-1,1,2))),"").
- Conditional formatting: 1=green progress done #22C55E, 2=light blue remaining #BFDBFE, 3=gold milestone #FACC15, 4=dark green completed #15803D.
- Additional rules: Delayed remaining=red, On Hold=gray, Not Started remaining=light gray. Today/Report Date column highlighted yellow.
- Freeze panes at J5 keeps task info visible while scrolling dates. Print-friendly column widths (4.5) for dates.
5. How to add a new task without breaking formulas or formatting:
- Insert a new row inside Tracker table (right-click > Insert Table Row). The Excel Table 'ProjectTable' will auto-expand and copy formulas for Duration, Conflict, Current State, Latest Pred End.
- Fill Task ID (e.g., T35), Phase (dropdown), Task Name, Description, Start, End, Predecessor, Dep Type, Resource, Status, Progress, Milestone flag, Milestone ID, Priority, Notes.
- Gantt: Insert row at same position (row 5+). Copy formulas from row above for cols A-I (Tracker links) and for date columns J:AR (bar formulas). Update tracker_row reference to match new Tracker row.
- Dashboard KPIs use COUNTA and COUNTIF over A2:A35 - extend ranges to include new rows (or convert to Table references). Charts will auto-update if you extend status/phase tables.
- Resources sheet: add new resource if needed; formulas COUNTIFS will include new tasks automatically.
6. How to interpret dashboard indicators and milestone markers:
- Dashboard!B2 = Report Date (editable, default TODAY). Controls Overdue/Active/Upcoming logic in Tracker!R and Gantt Today highlight.
- KPIs: Total, Completed, In Progress, Not Started, On Hold, Delayed, Overdue, Overall Progress (simple avg and weighted by duration), Milestones Completed/Remaining, Tasks with Conflict, Days Remaining.
- Charts: Pie 'Tasks by Status', Bar 'Tasks by Phase' and 'Avg Progress by Phase' dynamically linked to Tracker counts via COUNTIF/AVERAGEIF.
- Milestone sheet: Milestone Date, Linked Tasks, Avg Progress = AVERAGE(XLOOKUP(TEXTSPLIT(LinkedTasks),Tracker TaskID,Progress)). Completed? = Yes when avg=100%.
- Resources sheet: Assigned Tasks, Active, Completed, Outstanding, Avg Progress, Workload Flag (High load if >3 tasks, Potential overlap if multiple active).
- Conflict/Validation column: ✓ OK = no issue, ⚠ flags End<Start, Outside window, Pred conflict. Fix by adjusting dates or predecessors.
- Health: Completed = Progress 100%, Overdue = End < Report Date and Progress<100%, Active = Report Date between Start/End, Upcoming = Start > Report Date, At Risk = other.
7. Assumptions & Inferred Values:
- All dates, dependencies, milestones, resources, progress % extracted from Project_Plan_Essentials markdown. Progress marked [INFERRED] in source - preserved in Notes column.
- Priority column is INFERRED (not in source) - assigned based on critical path: Governance, PAB, RAG, Sandbox, IE, HITL, Outbound, Final verification = Critical.
- Milestone indicator YES flagged for tasks ending on milestone dates: T03,T04 (M1 09-14), T10 (M2 09-19), T14 (M3 09-23), T20,T21 (M4 10-02), T24 (M5 10-06), T29 (M6 10-10), T34 (M7 10-14).
- Description column synthesized from architecture doc and evidence notes - flagged as derived, not invented beyond source.
- Dependency Type = FS for all per spec Section 2.2 (Finish-to-Start).
- Calendar days inclusive (duration = End-Start+1).
- Missing: Platform API credentials, exact budget figures - noted in Milestones/Notes and assumed injected via vault during T25.

## Tracker
Task ID | Phase / Workstream | Task Name | Task Description | Start Date | End Date | Duration | Predecessor / Dependency | Dependency Type | Assigned Resource / Owner | Status | Progress % | Milestone (YES/NO) | Milestone ID | Priority | Notes | Conflict / Validation | Current State | Latest Pred End
T01 | Phase 1: Governance, Policy & Canonical State | Define enterprise objectives, tenant scopes, and budget boundaries | Define strategic objectives, tenant scopes, budgets, risk appetite. Input from Brand Stakeholder/Portfolio Owner. Output: approved scope envelope and budget boundaries per brand. Governed by Model A. | 2026-09-11 | 2026-09-12 |  | None | FS | Brand Stakeholder / Portfolio Owner | Completed | 100% | NO | M1 | Critical | Architectural scope, objectives, and budget envelopes established in source blueprint. [INFERRED: 100%]
T02 | Phase 1: Governance, Policy & Canonical State | Configure machine-readable policy rules, autonomy tiers, and claim limits | Configure machine-readable policy rules, autonomy tiers, claim limits, legal constraints in Enterprise Policy Engine. Versioned policy envelopes with tenant isolation. | 2026-09-11 | 2026-09-12 |  | None | FS | Enterprise Policy Engine | Completed | 100% | NO | M1 | Critical | Compliance rules, autonomy tiers, and brand constraints defined in policy engine specification. [INFERRED: 100%]
T03 | Phase 1: Governance, Policy & Canonical State | Establish Policy & Authorization Boundary (PAB) evaluation rules | Establish Policy & Authorization Boundary evaluation: caller ID, delegation chain, tenant scope, risk tier, monotonic attenuation, tool allowlisting. Security gate for all downstream. | 2026-09-12 | 2026-09-14 |  | T01, T02 | FS | Policy & Authorization Boundary (PAB) | Completed | 100% | YES | M1 | Critical | PAB monotonic attenuation logic and verification formulas validated in control plane. [INFERRED: 100%]
T04 | Phase 1: Governance, Policy & Canonical State | Initialize Canonical Task State Machine (CTS) and DAG execution schema | Initialize Canonical Task State Machine and DAG execution schema: lifecycle states CREATED→COMPLETED, checkpoints, holds, dependency locks, state ledger. | 2026-09-12 | 2026-09-14 |  | T01 | FS | Canonical Task State Machine (CTS) | Completed | 100% | YES | M1 | Critical | Canonical Task State Machine lifecycle states (CREATED to COMPLETED) configured. [INFERRED: 100%]
T05 | Phase 2: Governed Data Plane & Central Storage | Provision Central Enterprise Database (CDB) relational tables & vector stores | Provision Central Enterprise Database: relational tables, JSONB docs, vector namespaces, embeddings, state ledgers, telemetry time-series. System of record. | 2026-09-14 | 2026-09-16 |  | T04 | FS | Central Enterprise Database (CDB) | Completed | 100% | NO | M2 | High | Relational tables, JSONB schemas, and pgvector stores defined in Central DB model. [INFERRED: 100%]
T06 | Phase 2: Governed Data Plane & Central Storage | Connect Headless CMS content models and staging layout schemas | Connect Headless CMS content models and staging layout schemas: page models, catalog diffs, digital assets, staged schemas for W_DEV consumption. | 2026-09-14 | 2026-09-16 |  | T04 | FS | Headless CMS & Web Store (CMS) | Completed | 100% | NO | M2 | High | Headless CMS content schemas and staging layout diffs integrated. [INFERRED: 100%]
T07 | Phase 2: Governed Data Plane & Central Storage | Instantiate Institutional Memory Store (MEM) for brand heuristics & rules | Instantiate Institutional Memory Store for brand heuristics, voice rules, learned heuristics, long-term knowledge promotion from W_LEARN. | 2026-09-14 | 2026-09-16 |  | T04 | FS | Institutional Memory Store (MEM) | Completed | 100% | NO | M2 | High | Long-term institutional memory schemas and brand book namespaces established. [INFERRED: 100%]
T08 | Phase 2: Governed Data Plane & Central Storage | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | Configure Artifact & Evidence Registry for UUID/hash deliverables: content-addressable storage, SHA-256 validation, copy packs, code diffs, dossiers. | 2026-09-16 | 2026-09-18 |  | T05 | FS | Artifact & Evidence Registry (ART) | Completed | 100% | NO | M2 | Medium | Content-addressable artifact storage with UUID and SHA-256 hash validation defined. [INFERRED: 100%]
T09 | Phase 2: Governed Data Plane & Central Storage | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | Deploy Governed MCP Data Boundary CRUD gateways & connection pools: schema-validated read/write facades over CDB, CMS, MEM, ART. | 2026-09-16 | 2026-09-18 |  | T05, T06, T07 | FS | Governed MCP Data Boundary | Completed | 100% | NO | M2 | Critical | MCP Data Boundary read/write CRUD capability facades verified against storage layer. [INFERRED: 100%]
T10 | Phase 2: Governed Data Plane & Central Storage | Configure Agentic RAG Controller with tenant isolation & freshness gates | Configure Agentic RAG Controller with tenant isolation, freshness gates, provenance attestation, vector indexing. Exclusive broker under Model A. | 2026-09-18 | 2026-09-19 |  | T03, T09 | FS | Agentic RAG Controller | Completed | 100% | YES | M2 | Critical | Model A Agentic RAG Controller deployed with tenant-scoped filtering and provenance tagging. [INFERRED: 100%]
T11 | Phase 3: Sandbox Isolation & Sub-Agent Readiness | Deploy agent_sandbox with cgroups, seccomp, and tmpfs isolation | Deploy agent_sandbox with cgroups, seccomp, tmpfs isolation: micro-VM/container layer for all ephemeral sub-agents and micro-tools. | 2026-09-18 | 2026-09-20 |  | T03 | FS | Sandbox Controller (agent_sandbox) | Completed | 100% | NO | M3 | Critical | agent_sandbox (AIO Sandbox) virtualized container environment instantiated. [INFERRED: 100%]
T12 | Phase 3: Sandbox Isolation & Sub-Agent Readiness | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL) | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL): default deny, domain-whitelisted proxy for S_SCRAPE, block metadata endpoints. | 2026-09-20 | 2026-09-21 |  | T11 | FS | Sandbox Controller (agent_sandbox) | Completed | 100% | NO | M3 | High | Network egress firewall configured with default DENY_ALL policy and domain whitelist proxy. [INFERRED: 100%]
T13 | Phase 3: Sandbox Isolation & Sub-Agent Readiness | Implement sandbox execution audit interception to W3C PROV ledger | Implement sandbox execution audit interception to W3C PROV ledger: syscall, memory, exit code, stderr streaming to immutable audit log. | 2026-09-21 | 2026-09-22 |  | T11, T12 | FS | Sandbox Controller & W3C PROV Audit | Completed | 100% | NO | M3 | High | Sandbox execution interceptor piped directly to W3C PROV audit logging service. [INFERRED: 100%]
T14 | Phase 3: Sandbox Isolation & Sub-Agent Readiness | Instantiate specialist sub-agent micro-tools (S_CODE to S_ATTR) in sandbox | Instantiate specialist sub-agent micro-tools S_CODE to S_ATTR in sandbox: S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE, S_ATTR. | 2026-09-21 | 2026-09-23 |  | T11, T12 | FS | Specialist Sub-Agents (L4_SUBS) | Completed | 100% | YES | M3 | Critical | Specialist micro-tools (S_CODE through S_ATTR) containerized inside sandbox. [INFERRED: 100%]
T15 | Phase 4: Domain Intelligence & Asset Synthesis | Configure Intelligence Engine context assembly & brand persona layer | Configure Intelligence Engine context assembly & brand persona layer: dynamic context, task grants, brand persona, upward evidence synthesis gates. | 2026-09-23 | 2026-09-24 |  | T04, T10 | FS | Intelligence Engine (IE) | Completed | 100% | NO | M4 | Critical | Intelligence Engine context assembler and brand persona layer initialized. [INFERRED: 100%]
T16 | Phase 4: Domain Intelligence & Asset Synthesis | Ingest & verify product formulations and compliance dossiers (W_PROD) | Ingest & verify product formulations and compliance dossiers (W_PROD): clinical evidence mapping, regulatory claim linters via S_VAL. | 2026-09-24 | 2026-09-26 |  | T10, T14, T15 | FS | Product / Evidence Engine & S_VAL | Completed | 100% | NO | M4 | High | W_PROD specifications mapped and verified against regulatory claim linters (S_VAL). [INFERRED: 100%]
T17 | Phase 4: Domain Intelligence & Asset Synthesis | Ingest & parse customer support tickets and review sentiment (W_VOICE) | Ingest & parse customer support tickets and review sentiment (W_VOICE): sentiment vectors, objection clustering via S_PARSE. | 2026-09-24 | 2026-09-26 |  | T10, T14, T15 | FS | Customer Voice Engine & S_PARSE | Completed | 100% | NO | M4 | High | W_VOICE sentiment analysis and customer objection clustering completed (S_PARSE). [INFERRED: 100%]
T18 | Phase 4: Domain Intelligence & Asset Synthesis | Scrape competitor ad libraries, pricing, and market positioning (W_COMP) | Scrape competitor ad libraries, pricing, market positioning (W_COMP): price benchmarks, ad copy trends via S_SCRAPE with proxy allowlist. | 2026-09-24 | 2026-09-26 |  | T12, T14, T15 | FS | Competitor Intel Engine & S_SCRAPE | Completed | 100% | NO | M4 | High | W_COMP ad library scraping and competitor pricing benchmark extraction verified (S_SCRAPE). [INFERRED: 100%]
T19 | Phase 4: Domain Intelligence & Asset Synthesis | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT): media mix, funnel models, budget proposals via S_ALLOC. | 2026-09-26 | 2026-09-29 |  | T16, T17, T18 | FS | Strategy Engine & S_ALLOC | Completed | 100% | NO | M4 | Critical | W_STRAT omnichannel media mix, budget allocation, and funnel models formulated (S_ALLOC). [INFERRED: 100%]
T20 | Phase 4: Domain Intelligence & Asset Synthesis | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT): multi-channel copy, hooks, calendars via S_COPY, requires approved claims. | 2026-09-29 | 2026-10-02 |  | T16, T19 | FS | Creative & Content Engine & S_COPY | Completed | 100% | YES | M4 | High | W_CREAT ad copy variants, hooks, social calendars, and visual briefs generated (S_COPY). [INFERRED: 100%]
T21 | Phase 4: Domain Intelligence & Asset Synthesis | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV): UI components, layout templates, CMS schema changes via S_CODE. | 2026-09-26 | 2026-10-02 |  | T06, T14, T15 | FS | Development Engine & S_CODE | Completed | 100% | YES | M4 | Critical | W_DEV responsive UI templates, CMS schemas, and code diffs compiled (S_CODE). [INFERRED: 100%]
T22 | Phase 5: Evidence Consolidation & HITL | Consolidate worker evidence envelopes & verify confidence intervals | Consolidate worker evidence envelopes & verify confidence intervals: compile W_STRAT, W_CREAT, W_DEV outputs into validated evidence for IE. | 2026-10-02 | 2026-10-04 |  | T19, T20, T21 | FS | Intelligence Engine (IE) | In Progress | 50% | NO | M5 | Critical | Evidence envelopes consolidated; final confidence interval verification underway. [INFERRED: 50% - In Progress]
T23 | Phase 5: Evidence Consolidation & HITL | Generate structured action previews (spend, code diffs, claims, copy) | Generate structured action previews (spend, code diffs, claims, copy): formatted dossiers with artifact UUIDs for HITL review. | 2026-10-04 | 2026-10-05 |  | T22 | FS | Intelligence Engine (IE) | In Progress | 25% | NO | M5 | Critical | Action preview generator compiling spend proposals and code diff dossiers for HITL review. [INFERRED: 25% - In Progress]
T24 | Phase 5: Evidence Consolidation & HITL | Execute Human-in-the-Loop (HITL) quality, legal, and deploy sign-off | Execute Human-in-the-Loop quality, legal, and deploy sign-off: mandatory gate for spend, legal claims, code & deploys. Cryptographic signatures. | 2026-10-05 | 2026-10-06 |  | T23 | FS | Human-in-the-Loop (HITL) Gate | Not Started | 0% | YES | M5 | Critical | Awaiting formal Human-in-the-Loop review and cryptographic approval sign-off. [INFERRED: 0% - Planned]
T25 | Phase 6: Outbound Actuation & Go-Live | Initialize Outbound Actuation MCP Boundary with audience tokens | Initialize Outbound Actuation MCP Boundary with audience tokens: validate signed directives, audience tokens, dispatch to external surfaces. | 2026-10-06 | 2026-10-07 |  | T24 | FS | Outbound Actuation MCP Boundary | Not Started | 0% | NO | M6 | Critical | Outbound Actuation MCP Boundary standing by for signed execution directives. [INFERRED: 0%]
T26 | Phase 6: Outbound Actuation & Go-Live | Deploy live schemas, catalog updates & layout code to Website & CMS | Deploy live schemas, catalog updates & layout code to Website & CMS: push approved code diffs, catalog updates to headless CMS production. | 2026-10-07 | 2026-10-09 |  | T25 | FS | Outbound MCP & Website / CMS | Not Started | 0% | NO | M6 | High | Live website schema deployment and catalog push scheduled post-approval. [INFERRED: 0%]
T27 | Phase 6: Outbound Actuation & Go-Live | Publish ad campaigns and bid targets to Paid Ad Platforms | Publish ad campaigns and bid targets to Paid Ad Platforms: Meta, Google, TikTok campaigns via Outbound MCP with budget caps. | 2026-10-07 | 2026-10-09 |  | T25 | FS | Outbound MCP & Paid Ad Platforms | Not Started | 0% | NO | M6 | High | Paid ad campaign launch across Meta, Google, TikTok scheduled post-approval. [INFERRED: 0%]
T28 | Phase 6: Outbound Actuation & Go-Live | Publish scheduled social media posts and assets to Social Channels | Publish scheduled social media posts and assets to Social Channels: Instagram, X, YouTube scheduled posts via Outbound MCP. | 2026-10-07 | 2026-10-09 |  | T25 | FS | Outbound MCP & Social Channels | Not Started | 0% | NO | M6 | High | Social media publishing and scheduled content broadcast queued. [INFERRED: 0%]
T29 | Phase 6: Outbound Actuation & Go-Live | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs: attach listeners to live surfaces post go-live. | 2026-10-09 | 2026-10-10 |  | T26, T27, T28 | FS | Omnichannel Telemetry Engine | Not Started | 0% | YES | M6 | Critical | Omnichannel telemetry stream listeners and webhook endpoints queued for go-live. [INFERRED: 0%]
T30 | Phase 7: Telemetry Optimization & Closeout | Ingest live store traffic, checkout transactions & conversion logs into CDB | Ingest live store traffic, checkout transactions & conversion logs into CDB: real-time telemetry ingestion into Central DB. | 2026-10-10 | 2026-10-11 |  | T29 | FS | Telemetry Engine & Central Database | Not Started | 0% | NO | M7 | High | Live transaction, order event, and server log ingestion awaiting production traffic. [INFERRED: 0%]
T31 | Phase 7: Telemetry Optimization & Closeout | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN): attribution curves, fatigue scoring, ROAS optimization via S_ATTR. | 2026-10-11 | 2026-10-13 |  | T30 | FS | Learning Engine & S_ATTR | Not Started | 0% | NO | M7 | High | Multi-touch attribution modeling and creative decay scoring queued on telemetry feed. [INFERRED: 0%]
T32 | Phase 7: Telemetry Optimization & Closeout | Promote validated memory deltas into Institutional Memory and IE | Promote validated memory deltas into Institutional Memory and IE: promote learned heuristics and brand rule deltas from W_LEARN. | 2026-10-13 | 2026-10-14 |  | T31 | FS | Learning Engine, Memory Store & IE | Not Started | 0% | NO | M7 | Medium | Memory promotion of validated optimization deltas scheduled post-campaign run. [INFERRED: 0%]
T33 | Phase 7: Telemetry Optimization & Closeout | Validate end-to-end W3C PROV audit lineage, state integrity & logs | Validate end-to-end W3C PROV audit lineage, state integrity & logs: cryptographic sealing, tamper-evident verification of full execution trail. | 2026-10-13 | 2026-10-14 |  | T30, T31 | FS | W3C PROV Immutable Ledger | Not Started | 0% | NO | M7 | High | End-to-end W3C PROV audit trail verification and cryptographic sealing scheduled. [INFERRED: 0%]
T34 | Phase 7: Telemetry Optimization & Closeout | Perform final project verification against acceptance criteria & close | Perform final project verification against acceptance criteria & close: final verification, acceptance, contract closure on 2026-10-14. | 2026-10-14 | 2026-10-14 |  | T32, T33 | FS | Intelligence Engine & Brand Owner | Not Started | 0% | YES | M7 | Critical | Final project sign-off and contract closure scheduled for 2026-10-14. [INFERRED: 0% - Milestone M7]

## Gantt
Governed Multi-Brand Agentic System - Gantt Timeline (Sep 11 - Oct 14, 2026)
Task ID | Phase / Workstream | Task Name | Resource | Status | Progress % | Start Date | End Date | Milestone? | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
[9 empty] | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
[9 empty] | 09/11 | 09/12 | 09/13 | 09/14 | 09/15 | 09/16 | 09/17 | 09/18 | 09/19 | 09/20 | 09/21 | 09/22 | 09/23 | 09/24 | 09/25 | 09/26 | 09/27 | 09/28 | 09/29 | 09/30 | 10/01 | 10/02 | 10/03 | 10/04 | 10/05 | 10/06 | 10/07 | 10/08 | 10/09 | 10/10 | 10/11 | 10/12 | 10/13 | 10/14

## Dashboard
Project Dashboard - Governed Multi-Brand Agentic System
Reporting Date (controls Active/Overdue calculations): | 2026-09-10 | Project Window: 2026-09-11 to 2026-10-14 (34 days)
KPI | Value | Formula / Notes
Total Tasks |  | Count of tasks
Completed Tasks
In Progress Tasks
Not Started Tasks
On Hold Tasks
Delayed Tasks
Overdue (by date) |  | Based on Report Date
Overall Progress (simple avg) |  | Avg of Progress %
Overall Progress (weighted by duration) |  | Weighted
Milestones Completed
Milestones Remaining
Tasks with Conflict
Days Remaining
Tasks by Status |  |  | Tasks by Phase / Workstream
Status | Count |  | Phase | Count | Avg Progress
Not Started |  |  | Phase 1: Governance, Policy & Canonical State
In Progress |  |  | Phase 2: Governed Data Plane & Central Storage
Completed |  |  | Phase 3: Sandbox Isolation & Sub-Agent Readiness
On Hold |  |  | Phase 4: Domain Intelligence & Asset Synthesis
Delayed |  |  | Phase 5: Evidence Consolidation & HITL
Phase 6: Outbound Actuation & Go-Live
Upcoming Deadlines (Next 7 days from Report Date) |  |  | Phase 7: Telemetry Optimization & Closeout
Task ID | Task Name | End Date | Status | Progress

## Milestones
Milestone ID | Milestone Name | Milestone Date | Linked Tasks | Status | Avg Progress of Linked Tasks | Completed? | Description
M1 | Governance, Policy & Canonical State Initialization | 2026-09-14 | T01, T02, T03, T04 | Complete |  |  | Governance policies, PAB rules, CTS DAG ready
M2 | Governed Data Plane & Central Storage Integration (Model A) | 2026-09-19 | T05, T06, T07, T08, T09, T10 | Complete |  |  | CDB, CMS, MEM, ART, MCP Gateway, Agentic RAG
M3 | Sandbox Isolation & Specialist Sub-Agent Readiness | 2026-09-23 | T11, T12, T13, T14 | Complete |  |  | agent_sandbox, proxy, audit, sub-agent tools
M4 | Domain Intelligence Ingestion & Asset Synthesis Complete | 2026-10-02 | T15, T16, T17, T18, T19, T20, T21 | Complete |  |  | IE context, W_PROD/VOICE/COMP/STRAT/CREAT/DEV outputs
M5 | HITL Gateway Clearance & Cryptographic Authorization | 2026-10-06 | T22, T23, T24 | In Progress |  |  | Evidence consolidation, action previews, HITL sign-off
M6 | Outbound Actuation, Telemetry & Omnichannel Go-Live | 2026-10-10 | T25, T26, T27, T28, T29 | Planned |  |  | Outbound MCP, Website, Ads, Social, Telemetry hooks
M7 | Closed-Loop Telemetry Optimization & Final Project Closeout | 2026-10-14 | T30, T31, T32, T33, T34 | Planned |  |  | Live ingestion, attribution, memory promotion, audit close

## Resources
Resource Name | Assigned Tasks | Active Tasks | Completed Tasks | Outstanding Tasks | Avg Progress | Workload Flag | Tasks List
Brand Stakeholder / Portfolio Owner | 1 | [5 empty] | T01
Enterprise Policy Engine | 1 | [5 empty] | T02
Policy & Authorization Boundary (PAB) | 1 | [5 empty] | T03
Canonical Task State Machine (CTS) | 1 | [5 empty] | T04
Central Enterprise Database (CDB) | 1 | [5 empty] | T05
Headless CMS & Web Store (CMS) | 1 | [5 empty] | T06
Institutional Memory Store (MEM) | 1 | [5 empty] | T07
Artifact & Evidence Registry (ART) | 1 | [5 empty] | T08
Governed MCP Data Boundary | 1 | [5 empty] | T09
Agentic RAG Controller | 1 | [5 empty] | T10
Sandbox Controller (agent_sandbox) | 2 | [5 empty] | T11, T12
Sandbox Controller & W3C PROV Audit | 1 | [5 empty] | T13
Specialist Sub-Agents (L4_SUBS) | 1 | [5 empty] | T14
Intelligence Engine (IE) | 3 | [5 empty] | T15, T22, T23
Product / Evidence Engine & S_VAL | 1 | [5 empty] | T16
Customer Voice Engine & S_PARSE | 1 | [5 empty] | T17
Competitor Intel Engine & S_SCRAPE | 1 | [5 empty] | T18
Strategy Engine & S_ALLOC | 1 | [5 empty] | T19
Creative & Content Engine & S_COPY | 1 | [5 empty] | T20
Development Engine & S_CODE | 1 | [5 empty] | T21
Human-in-the-Loop (HITL) Gate | 1 | [5 empty] | T24
Outbound Actuation MCP Boundary | 1 | [5 empty] | T25
Outbound MCP & Website / CMS | 1 | [5 empty] | T26
Outbound MCP & Paid Ad Platforms | 1 | [5 empty] | T27
Outbound MCP & Social Channels | 1 | [5 empty] | T28
Omnichannel Telemetry Engine | 1 | [5 empty] | T29
Telemetry Engine & Central Database | 1 | [5 empty] | T30
Learning Engine & S_ATTR | 1 | [5 empty] | T31
Learning Engine, Memory Store & IE | 1 | [5 empty] | T32
W3C PROV Immutable Ledger | 1 | [5 empty] | T33
Intelligence Engine & Brand Owner | 1 | [5 empty] | T34

## Lists
Status | Priority | DepType | Phase | MilestoneYN | MilestoneID
Not Started | Critical | FS | Phase 1: Governance, Policy & Canonical State | YES | M1
In Progress | High | SS | Phase 2: Governed Data Plane & Central Storage | NO | M2
Completed | Medium | FF | Phase 3: Sandbox Isolation & Sub-Agent Readiness |  | M3
On Hold | Low | SF | Phase 4: Domain Intelligence & Asset Synthesis |  | M4
Delayed |  |  | Phase 5: Evidence Consolidation & HITL |  | M5
|  |  | Phase 6: Outbound Actuation & Go-Live |  | M6
|  |  | Phase 7: Telemetry Optimization & Closeout |  | M7