## Project Tracker
Governed Multi-Brand Agentic System — Master Project Tracker
Fixed Project Window: 2026-09-11 to 2026-10-14 ¦ Access Model: Model A ¦ Execution Boundary: agent_sandbox
Task ID | Phase | Task Name | Description | Start Date | End Date | Duration | Predecessor | Dependency Type | Milestone | Resource / Owner | Priority | Status | Progress % | Schedule Health | Notes
T01 | Phase 1: Governance & Authority | Define enterprise objectives, tenant scopes, and budget boundaries | Establish multi-brand goals, risk boundaries, and financial limits in governance console. | 2026-09-11 | 2026-09-12 |  | None | FS | No | Brand Stakeholder / Portfolio Owner | High | Not Started | 0% |  | Model A baseline; blueprint marked as complete; initialized at 0% for live execution tracking.
T02 | Phase 1: Governance & Authority | Configure machine-readable policy rules, autonomy tiers, and claim limits | Deploy enterprise compliance matrix and statutory guidelines to policy store. | 2026-09-11 | 2026-09-12 |  | None | FS | No | Enterprise Policy Engine | High | Not Started | 0% |  | Defines strict monotonic attenuation constraints for worker tools.
T03 | Phase 1: Governance & Authority | Establish Policy & Authorization Boundary (PAB) evaluation rules | Implement caller token, delegation chain, tenant scope, and attenuation validator. | 2026-09-12 | 2026-09-14 |  | T01, T02 | FS | No | Policy & Authorization Boundary (PAB) | High | Not Started | 0% |  | Same-day handoff from T01/T02 on 2026-09-12 [INFERRED].
T04 | Phase 1: Governance & Authority | Initialize Canonical Task State Machine (CTS) and DAG execution schema | Configure task state transitions, checkpoint barriers, dependency locks, and hold queues. | 2026-09-12 | 2026-09-14 |  | T01 | FS | No | Canonical Task State Machine (CTS) | High | Not Started | 0% |  | Authoritative single-source state ledger for Orchestrator.
M01 | Phase 1: Governance & Authority | Milestone 1: Governance, Policy & Canonical State Initialized | Verification of governance plane, attenuation rules, and state DAG machine. | 2026-09-14 | 2026-09-14 |  | T01, T02, T03, T04 | FS | Yes | Intelligence Engine & Owner | High | Not Started | 0% |  | Explicit checkpoint M1.
T05 | Phase 2: Governed Data Plane | Provision Central Enterprise Database (CDB) relational tables & vector stores | Deploy PostgreSQL, pgvector partitions, tenant schemas, and telemetry tables. | 2026-09-14 | 2026-09-16 |  | T04 | FS | No | Central Enterprise Database (CDB) | High | Not Started | 0% |  | Universal persistence target for all pipeline events.
T06 | Phase 2: Governed Data Plane | Connect Headless CMS content models and staging layout schemas | Establish CMS staged page models, catalog structures, and digital asset repositories. | 2026-09-14 | 2026-09-16 |  | T04 | FS | No | Headless CMS & Web Store (CMS) | Medium | Not Started | 0% |  | System of record for staged storefront layouts and catalog diffs.
T07 | Phase 2: Governed Data Plane | Instantiate Institutional Memory Store (MEM) for brand heuristics & rules | Configure long-term key-value and vector feature store for brand persona memory. | 2026-09-14 | 2026-09-16 |  | T04 | FS | No | Institutional Memory Store (MEM) | Medium | Not Started | 0% |  | Durable store for promoted optimization heuristics.
T08 | Phase 2: Governed Data Plane | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | Set up content-addressable storage for code patches, copy packs, and proof dossiers. | 2026-09-16 | 2026-09-18 |  | T05 | FS | No | Artifact & Evidence Registry (ART) | Medium | Not Started | 0% |  | SHA-256 and UUID delivery addressing.
T09 | Phase 2: Governed Data Plane | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | Expose standardized read/write capability facades to storage planes under strict schema validation. | 2026-09-16 | 2026-09-18 |  | T05, T06, T07 | FS | No | Governed MCP Data Boundary | High | Not Started | 0% |  | Exclusively accessible by Agentic RAG Controller.
T10 | Phase 2: Governed Data Plane | Configure Agentic RAG Controller with tenant isolation & freshness gates | Deploy hybrid semantic search, BM25 ranking, provenance tagging, and freshness verifiers. | 2026-09-18 | 2026-09-19 |  | T03, T09 | FS | No | Agentic RAG Controller | High | Not Started | 0% |  | Model A mandate: Exclusively queried by Intelligence Engine.
M02 | Phase 2: Governed Data Plane | Milestone 2: Governed Data Plane & Central Storage Integration (Model A) | Data boundary gateways, RAG controller, and enterprise stores validated. | 2026-09-19 | 2026-09-19 |  | T05, T06, T07, T08, T09, T10 | FS | Yes | Intelligence Engine & Agentic RAG | High | Not Started | 0% |  | Explicit checkpoint M2.
T11 | Phase 3: Sandbox Isolation | Deploy agent_sandbox with cgroups, seccomp, and tmpfs isolation | Configure virtualized micro-containers, memory scrubbing, and ephemeral process fences. | 2026-09-18 | 2026-09-20 |  | T03 | FS | No | Sandbox Controller (agent_sandbox) | High | Not Started | 0% |  | Isolated container/micro-VM layer beneath Worker Agents.
T12 | Phase 3: Sandbox Isolation | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL) | Enforce default deny network egress; whitelist explicit scraping target domains. | 2026-09-20 | 2026-09-21 |  | T11 | FS | No | Sandbox Controller (agent_sandbox) | High | Not Started | 0% |  | Prevents lateral token leakage and unauthorized internal scanning.
T13 | Phase 3: Sandbox Isolation | Implement sandbox execution audit interception to W3C PROV ledger | Stream syscall traces, execution exit codes, and resource metrics to audit ledger. | 2026-09-21 | 2026-09-22 |  | T11, T12 | FS | No | Sandbox Controller & W3C PROV Audit | Medium | Not Started | 0% |  | Guarantees forensic non-repudiation for all dynamic code runs.
T14 | Phase 3: Sandbox Isolation | Instantiate specialist sub-agent micro-tools (S_CODE to S_ATTR) in sandbox | Containerize S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE, S_ATTR micro-tools. | 2026-09-21 | 2026-09-23 |  | T11, T12 | FS | No | Specialist Sub-Agents (L4_SUBS) | High | Not Started | 0% |  | Ephemeral sub-agents execute strictly within sandbox boundary.
M03 | Phase 3: Sandbox Isolation | Milestone 3: Sandbox Isolation & Specialist Sub-Agent Readiness | Secure micro-virtualization runtime and specialist tools certified. | 2026-09-23 | 2026-09-23 |  | T11, T12, T13, T14 | FS | Yes | Sandbox Controller (agent_sandbox) | High | Not Started | 0% |  | Explicit checkpoint M3.
T15 | Phase 4: Domain Intelligence | Configure Intelligence Engine context assembly & brand persona layer | Initialize dynamic prompt assembler, token budgeter, and DAG task grant scheduler. | 2026-09-23 | 2026-09-24 |  | T04, T10 | FS | No | Intelligence Engine (IE) | High | Not Started | 0% |  | Controls context slices dispatched to worker engines.
T16 | Phase 4: Domain Intelligence | Ingest & verify product formulations and compliance dossiers (W_PROD) | Parse clinical claims, regulatory constraints, and formulation specs via S_VAL linter. | 2026-09-24 | 2026-09-26 |  | T10, T14, T15 | FS | No | Product / Evidence Engine & S_VAL | High | Not Started | 0% |  | Generates verified evidence dossiers.
T17 | Phase 4: Domain Intelligence | Ingest & parse customer support tickets and review sentiment (W_VOICE) | Extract CX sentiment vectors, pain-point clusters, and objection profiles via S_PARSE. | 2026-09-24 | 2026-09-26 |  | T10, T14, T15 | FS | No | Customer Voice Engine & S_PARSE | Medium | Not Started | 0% |  | Feeds customer objection vectors into strategy engine.
T18 | Phase 4: Domain Intelligence | Scrape competitor ad libraries, pricing, and market positioning (W_COMP) | Execute whitelisted proxy DOM scraping of rival ad creatives and price points via S_SCRAPE. | 2026-09-24 | 2026-09-26 |  | T12, T14, T15 | FS | No | Competitor Intel Engine & S_SCRAPE | Medium | Not Started | 0% |  | Strict outbound proxy allowlist enforced.
T19 | Phase 4: Domain Intelligence | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | Simulate funnel trajectories and media mix spend distributions via S_ALLOC micro-tool. | 2026-09-26 | 2026-09-29 |  | T16, T17, T18 | FS | No | Strategy Engine & S_ALLOC | High | Not Started | 0% |  | Synthesizes product claims, customer voice, and rival intel.
T20 | Phase 4: Domain Intelligence | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | Produce grounded copy packs, video scripts, and social hooks using S_COPY variant generator. | 2026-09-29 | 2026-10-02 |  | T16, T19 | FS | No | Creative & Content Engine & S_COPY | High | Not Started | 0% |  | All copy strictly grounded in W_PROD compliance dossiers.
T21 | Phase 4: Domain Intelligence | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | Build storefront AST diffs, Tailwind components, and CMS JSON schemas using S_CODE linter. | 2026-09-26 | 2026-10-02 |  | T06, T14, T15 | FS | No | Development Engine & S_CODE | High | Not Started | 0% |  | 7-day execution running in parallel with strategy and copy work.
M04 | Phase 4: Domain Intelligence | Milestone 4: Domain Intelligence Ingestion & Asset Synthesis Complete | Multichannel marketing roadmap, copy packs, and UI templates assembled. | 2026-10-02 | 2026-10-02 |  | T15, T16, T17, T18, T19, T20, T21 | FS | Yes | Intelligence Engine & Worker Agents | High | Not Started | 0% |  | Explicit checkpoint M4.
T22 | Phase 5: Synthesis & HITL Gate | Consolidate worker evidence envelopes & verify confidence intervals | Synthesize upward evidence envelopes and check citation confidence scores in Orchestrator. | 2026-10-02 | 2026-10-04 |  | T19, T20, T21 | FS | No | Intelligence Engine (IE) | High | Not Started | 0% |  | Pre-verification before human presentation.
T23 | Phase 5: Synthesis & HITL Gate | Generate structured action previews (spend, code diffs, claims, copy) | Compile human-readable action dossiers with side-by-side diffs and spend impact models. | 2026-10-04 | 2026-10-05 |  | T22 | FS | No | Intelligence Engine (IE) | High | Not Started | 0% |  | Mandatory input payload for HITL clearance.
T24 | Phase 5: Synthesis & HITL Gate | Execute Human-in-the-Loop (HITL) quality, legal, and deploy sign-off | Formal stakeholder review and cryptographic authorization of ad spend, copy, and code. | 2026-10-05 | 2026-10-06 |  | T23 | FS | No | Human-in-the-Loop (HITL) Gate | High | Not Started | 0% |  | Hard stop rule: Zero external actuation permitted without signature.
M05 | Phase 5: Synthesis & HITL Gate | Milestone 5: HITL Gateway Clearance & Cryptographic Authorization | Human stakeholder approvals recorded and signed. | 2026-10-06 | 2026-10-06 |  | T22, T23, T24 | FS | Yes | Human-in-the-Loop (HITL) Gate | High | Not Started | 0% |  | Explicit checkpoint M5.
T25 | Phase 6: Outbound Actuation | Initialize Outbound Actuation MCP Boundary with audience tokens | Validate post-HITL approval tokens, rate limiters, and payload dispatch signatures. | 2026-10-06 | 2026-10-07 |  | T24 | FS | No | Outbound Actuation MCP Boundary | High | Not Started | 0% |  | Audience token injection [MISSING credentials vault].
T26 | Phase 6: Outbound Actuation | Deploy live schemas, catalog updates & layout code to Website & CMS | Execute live schema migrations, publish page templates, and push product catalog diffs. | 2026-10-07 | 2026-10-09 |  | T25 | FS | No | Outbound MCP & Website / CMS | High | Not Started | 0% |  | Actuation into live production digital storefront.
T27 | Phase 6: Outbound Actuation | Publish ad campaigns and bid targets to Paid Ad Platforms | Upload campaign ad sets, targeting matrices, and budget caps to Meta, Google, and TikTok APIs. | 2026-10-07 | 2026-10-09 |  | T25 | FS | No | Outbound MCP & Paid Ad Platforms | High | Not Started | 0% |  | Multi-channel paid media activation.
T28 | Phase 6: Outbound Actuation | Publish scheduled social media posts and assets to Social Channels | Schedule and dispatch content calendars to Instagram, X, TikTok, and YouTube endpoints. | 2026-10-07 | 2026-10-09 |  | T25 | FS | No | Outbound MCP & Social Channels | Medium | Not Started | 0% |  | Organic omnichannel distribution.
T29 | Phase 6: Outbound Actuation | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | Activate real-time server webhook endpoints, pixel listeners, and order tracking pipelines. | 2026-10-09 | 2026-10-10 |  | T26, T27, T28 | FS | No | Omnichannel Telemetry Engine | High | Not Started | 0% |  | Establishes closed-loop real-time telemetry stream.
M06 | Phase 6: Outbound Actuation | Milestone 6: Outbound Actuation, Telemetry & Omnichannel Go-Live | Storefront live, ad campaigns publishing, and real-time telemetry active. | 2026-10-10 | 2026-10-10 |  | T25, T26, T27, T28, T29 | FS | Yes | Outbound MCP & Operations | High | Not Started | 0% |  | Explicit checkpoint M6.
T30 | Phase 7: Closed-Loop Telemetry | Ingest live store traffic, checkout transactions & conversion logs into CDB | Capture live clickstream, conversion events, and ad attribution pings into timeseries tables. | 2026-10-10 | 2026-10-11 |  | T29 | FS | No | Telemetry Engine & Central Database | High | Not Started | 0% |  | Continuous persistent stream into PostgreSQL/Timescale.
T31 | Phase 7: Closed-Loop Telemetry | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | Execute attribution decay models and creative fatigue analysis via S_ATTR micro-tool. | 2026-10-11 | 2026-10-13 |  | T30 | FS | No | Learning Engine & S_ATTR | High | Not Started | 0% |  | Computes budget reallocation deltas.
T32 | Phase 7: Closed-Loop Telemetry | Promote validated memory deltas into Institutional Memory and IE | Write high-confidence performance heuristics into Institutional Memory Store (MEM). | 2026-10-13 | 2026-10-14 |  | T31 | FS | No | Learning Engine, Memory Store & IE | Medium | Not Started | 0% |  | Completes closed-loop learning optimization.
T33 | Phase 7: Closed-Loop Telemetry | Validate end-to-end W3C PROV audit lineage, state integrity & logs | Cryptographically verify audit trails from IE, PAB, HITL, RAG, Sandbox, and MCP gates. | 2026-10-13 | 2026-10-14 |  | T30, T31 | FS | No | W3C PROV Immutable Ledger | High | Not Started | 0% |  | Tamper-evident W3C PROV compliance validation.
T34 | Phase 7: Closed-Loop Telemetry | Perform final project verification against acceptance criteria & close | Formal executive sign-off, SLA certification, and multi-brand system delivery. | 2026-10-14 | 2026-10-14 |  | T32, T33 | FS | No | Intelligence Engine & Brand Owner | High | Not Started | 0% |  | Project finish on 2026-10-14.
M07 | Phase 7: Closed-Loop Telemetry | Milestone 7: Closed-Loop Telemetry Optimization & Final Project Closeout | Attribution optimized, memory updated, ledger sealed, and system accepted. | 2026-10-14 | 2026-10-14 |  | T30, T31, T32, T33, T34 | FS | Yes | Brand Stakeholder & IE | High | Not Started | 0% |  | Explicit checkpoint M7 (Project Complete).
Formulas:
Schedule Health = IF([Milestone]="Yes",IF([Progress %]=1,"Completed",IF(TODAY()>[End Date],"Overdue","Scheduled")),IF([Progress %]=1,"Completed",IF([Status]="Delayed","Delayed",IF([Status]="On Hold","On Hold",IF(TODAY()>[End Date],"Overdue",IF(AND(TODAY()>=[Start Date],[Progress %]=0),"Behind Schedule","On Track"))))))

## Gantt
Governed Multi-Brand Agentic System — Automated Timeline Visualization
Schedule Duration: 2026-09-11 to 2026-10-14 (34 Calendar Days) ¦ Legend: ■ Done (Blue) ¦ ░ Remaining (Light Blue) ¦ ◆ Milestone (Gold) | [5 empty] | September 2026 (Launch & Foundation Plane) | [19 empty] | October 2026 (Actuation & Closed-Loop Telemetry)
Task ID | Task Name | Start Date | End Date | Progress % | Milestone | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE

## Dashboard
Governed Multi-Brand Agentic System — Executive Program Dashboard
Live Project Window: 2026-09-11 to 2026-10-14 ¦ All Metrics Update Dynamically via Structured Formulas
TOTAL TASKS |  | COMPLETED TASKS |  | IN-PROGRESS TASKS |  | NOT STARTED | OVERALL PROGRESS
TOTAL MILESTONES |  | CLEARED MILESTONES |  | REMAINING MILESTONES |  | PROJECT WINDOW | DAYS REMAINING
Workstream Status Breakdown |  |  |  | Phase Execution & Governance Health
Status | Task Count | % of Total |  | Phase / Workstream | Tasks | Avg Progress
Not Started |  |  |  | Phase 1: Governance & Authority
In Progress |  |  |  | Phase 2: Governed Data Plane
Completed |  |  |  | Phase 3: Sandbox Isolation
On Hold |  |  |  | Phase 4: Domain Intelligence
Delayed |  |  |  | Phase 5: Synthesis & HITL Gate
Phase 6: Outbound Actuation
Phase 7: Closed-Loop Telemetry
Key Program Milestones & Status
Milestone ID | Checkpoint Name | Scheduled Date | Status | Health

## Resources
Governed Multi-Brand Agentic System — Resource Matrix & Utilization
Aggregates workload across human owners, control nodes, worker agents, and sandbox components
Resource Name | Total Assigned Tasks | Completed | In Progress | Remaining | Average Progress | Operational Role & Allocation Notes
Brand Stakeholder / Portfolio Owner | [5 empty] | Governance authority; strategic directive inputs at project launch and acceptance sign-off at project close.
Enterprise Policy Engine | [5 empty] | Automated compliance engine; versioned policy envelope publication and tenant claim boundary enforcement.
Policy & Authorization Boundary (PAB) | [5 empty] | Security proxy; caller ID evaluation, monotonic attenuation verification, and cryptographic delegation checks.
Canonical Task State Machine (CTS) | [5 empty] | Control state engine; maintains task DAG transitions, hold gates, and dependency locks.
Central Enterprise Database (CDB) | [5 empty] | Persistent system of record; relational tables, vector spaces, and timeseries telemetry ingestion.
Headless CMS & Web Store (CMS) | [5 empty] | Content store; staged page layout schemas, catalog diffs, and production frontend models.
Institutional Memory Store (MEM) | [5 empty] | Institutional knowledge base; promoted heuristics, brand persona parameters, and optimization weights.
Artifact & Evidence Registry (ART) | [5 empty] | Content-addressable storage; UUID and SHA-256 versioned diffs, proof dossiers, and asset packs.
Governed MCP Data Boundary | [5 empty] | Protocol capability gateway; CRUD adapters and schema-validated access to enterprise storage.
Agentic RAG Controller | [5 empty] | Exclusive Model A data retrieval broker for the Intelligence Engine; semantic search & freshness checks.
Sandbox Controller (agent_sandbox) | [5 empty] | Micro-virtualization boundary; cgroups memory limits, seccomp profiles, and strict egress proxying.
Specialist Sub-Agents (L4_SUBS) | [5 empty] | Ephemeral micro-tools (S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE, S_ATTR) executed in sandbox.
Intelligence Engine (IE) | [5 empty] | Central Orchestrator; context assembly, DAG execution, upward evidence synthesis, and action previews.
Product / Evidence Engine & S_VAL | [5 empty] | Domain worker; clinical trial extraction, regulatory claim validation, and formulation specifications.
Customer Voice Engine & S_PARSE | [5 empty] | Domain worker; CX ticket ingestion, sentiment clustering, and customer objection mapping.
Competitor Intel Engine & S_SCRAPE | [5 empty] | Domain worker; proxy-mediated ad library scraping, price tracking, and positioning analysis.
Strategy Engine & S_ALLOC | [5 empty] | Domain worker; multi-brand marketing roadmaps, budget allocation modeling, and funnel planning.
Creative & Content Engine & S_COPY | [5 empty] | Domain worker; multi-variant copy generation, hook drafting, and visual brief formatting.
Development Engine & S_CODE | [5 empty] | Domain worker; storefront components, AST code linting, CMS schemas, and pull request diffs.
Human-in-the-Loop (HITL) Gate | [5 empty] | Quality gatekeeper; mandatory human clearance for marketing spend, legal claims, and code deployment.
Outbound Actuation MCP Boundary | [5 empty] | Security egress gateway; audience token injection, cryptographic signing, and rate-limited API dispatch.
Omnichannel Telemetry Engine | [5 empty] | Real-time event ingestor; webhooks, pixel triggers, conversion telemetry, and server log streams.
Learning & Performance Engine & S_ATTR | [5 empty] | Domain worker; multi-touch attribution, creative decay estimation, and ROAS optimization.
W3C PROV Immutable Ledger | [5 empty] | Tamper-evident audit store; W3C PROV entity-activity-agent relationships and execution lineage.

## Assumptions & Gaps
Governed Multi-Brand Agentic System — Architectural Assumptions & Gaps
Formal reconciliation audit categorized by standard governance labels
Classification Label | Source Field / Item | Identified Condition / Architectural Context | Resolution Implemented in Workbook | User / Stakeholder Action Needed
[CONFLICT] | System Architecture Flowcharts | Comparison between Final-Level Full Architecture.md and flowchart.drawio.html. | Zero architectural conflicts identified. The Draw.io XML contains the identical Mermaid syntax and layer groupings. | None. System topology is 100% verified and structurally consistent.
[INFERRED] | Task Calendar Scheduling | Architectural specifications define DAG flow and component interactions without explicit calendar dates. | Inferred continuous dates across the fixed 34-day project window (2026-09-11 to 2026-10-14) respecting all DAG dependencies. | Review inferred task sequencing; adjust individual Start/End dates if team availability shifts.
[INFERRED] | Baseline Progress Protocol | Blueprint indicates foundational specifications are established, but operational project requires live tracking. | All tasks initialized at 0% with 'Not Started' status to allow live tracking from day one; baseline readiness documented in notes. | Update Progress % in Project Tracker as implementation milestones are executed.
[INFERRED] | Finish-to-Start Same-Day Handoffs | Successive tasks share boundary dates (e.g., T01/T02 finish on Sept 12 while T03/T04 start on Sept 12). | Treated as valid same-day handoffs where predecessor deliverables unblock successor initialization within the same working day. | Confirm operational teams are prepared for intra-day handoffs at Phase transition points.
[MISSING] | External Platform Credentials | API keys, OAuth tokens, and staging credentials for Meta Ads, Google Ads, TikTok, and CMS production are omitted. | Assumed that credentials will be injected via enterprise secret management vaults into Outbound MCP Boundary during T25. | Security team must provision cryptographic secrets and audience tokens in key vaults prior to Phase 6.
[MISSING] | Exact Financial Spend Caps | Data flow diagrams reference spend limits and media budgets conceptually without discrete currency numbers. | Structured action preview generator (T23) is designed to ingest exact budget envelopes defined by Brand Owner in T01. | Brand Portfolio Owner must supply numerical budget ceilings during Task T01 kickoff.
[OUTSIDE WINDOW] | Project Window Conformance | Verification of all 34 tasks and 7 milestones against fixed window (2026-09-11 to 2026-10-14). | Zero tasks scheduled outside the allowed project window. Earliest start is Sept 11, 2026; latest end is Oct 14, 2026. | None. Schedule conforms strictly to the 34-calendar-day mandate.
[DEPENDENCY ISSUE] | DAG Integrity Verification | Audit of direct predecessor and successor relationships across the multi-tier engine hierarchy. | Zero dependency cycles or orphan nodes exist. Authority monotonically decreases down the delegation tree. | Maintain Model A broker exclusivity when modifying task dependencies.

## Instructions
Governed Multi-Brand Agentic System — Standard Operating Instructions
Operational guide for editing, updating progress, maintaining dependencies, and tracking schedules
Instruction Topic | Standard Operating Protocol | Impact on Formulas & Sheets | Best Practice Guidance
1. Where to Edit Tasks | Edit tasks strictly in Sheet 1 ('Project Tracker'). Columns A through F, H, I, J, K, L, M, N, and P accept user inputs. | Changes automatically propagate to Sheet 2 ('Gantt'), Sheet 3 ('Dashboard'), and Sheet 4 ('Resources'). | Never type over calculated columns (Column G: Duration, Column O: Schedule Health).
2. How to Change Dates | Enter dates in 'YYYY-MM-DD' format in Start Date (Col E) and End Date (Col F). | Duration automatically recalculates via formula (=[@End]-[@Start]+1). Gantt timeline bars adjust length. | Ensure Start Date <= End Date. Stay within project bounds (2026-09-11 to 2026-10-14).
3. How to Update Progress % | Type a percentage (e.g., 50%) or decimal (e.g., 0.50) into Progress % (Col N). Cell is validated for 0.0 to 1.0. | Gantt fills the completed duration bar with dark blue blocks ('█') based on the percentage entered. | When progress reaches 100%, update Status to 'Completed' to sync health indicators.
4. How to Change Status | Select Status from the Data Validation dropdown in Col M (Not Started, In Progress, Completed, On Hold, Delayed). | Reconciles with Schedule Health (Col O) and updates Dashboard KPI cards and status breakdown table. | If a task is blocked, mark as 'On Hold' or 'Delayed' rather than artificially changing dates.
5. How to Assign Resources | Select or enter the responsible entity in Col K. Use approved roster names to ensure proper resource aggregation. | Updates assigned task counts, completion rates, and average progress in Sheet 4 ('Resources'). | For joint ownership, enter comma-separated entities (e.g., 'Intelligence Engine & Brand Owner').
6. Adding or Modifying Dependencies | Update Predecessor IDs in Col H (e.g., 'T01, T02') and select Dependency Type in Col I (FS, SS, FF, SF). | Maintains the Directed Acyclic Graph (DAG). Does not alter dates automatically but guides schedule integrity. | Successor start dates should never precede the completion date of their finish-to-start predecessors.
7. Adding a New Task Safely | Right-click inside 'ProjectTrackerTable' above row 45 and select Insert > Table Rows Above. | Formulas in Duration and Schedule Health, as well as Data Validation rules, expand automatically. | Assign a unique Task ID (e.g., T35). Update Gantt row links to maintain alignment.
8. Milestone Markers | Set Milestone to 'Yes' in Col J. Set Start Date equal to End Date (e.g., 2026-09-14). | Gantt renders a gold diamond symbol ('◆') instead of a duration bar; row highlights yellow. | Milestones are tracked separately in Dashboard KPI cards and Milestone clearance schedules.
9. Dynamic Gantt Behavior | Sheet 2 ('Gantt') is 100% formula-driven from 'Project Tracker' across 34 continuous calendar days. | No manual coloring needed. Completed portions show as '█' (solid blue), remaining as '░' (light blue). | Weekend days (Sat/Sun) feature dedicated shading in timeline header rows 4 and 5.
10. Dashboard Health Indicators | Sheet 3 ('Dashboard') aggregates all active task data using COUNTIFS and AVERAGEIFS. | Health shows 'On Track' (normal), 'Behind Schedule' (start elapsed with 0%), 'Overdue' (end elapsed), or 'Complete'. | Review the 'Key Program Milestones' table on the Dashboard weekly to ensure delivery on schedule.