## Project Tracker
Task ID | Phase | Task Name | Description | Start Date | End Date | Duration | Predecessor | Dependency Type | Milestone | Resource / Owner | Priority | Status | Progress % | Schedule Health | Notes | Dep Constraint
T01 | P1 · Governance & Policy | Define enterprise objectives, tenant scopes & budget boundaries | Capture objectives, tenant scopes, budget caps and risk appetite. | 2026-09-11 | 2026-09-12 |  |  | FS | No | Brand Stakeholder / Portfolio Owner | High | Not Started | 0% |  | [INFERRED] dates
T02 | P1 · Governance & Policy | Configure machine-readable policy rules, autonomy tiers & claim limits | Encode policy, legal rules and claim boundaries. | 2026-09-11 | 2026-09-12 |  |  | FS | No | Enterprise Policy Engine | High | Not Started | 0% |  | [INFERRED] dates
T03 | P1 · Governance & Policy | Establish Policy & Authorization Boundary (PAB) evaluation rules | Caller-ID, delegation chain, tenant scope, risk tier checks. | 2026-09-12 | 2026-09-14 |  | T01, T02 | FS | No | Policy & Authorization Boundary (PAB) | High | Not Started | 0%
T04 | P1 · Governance & Policy | Initialize Canonical Task State Machine (CTS) & DAG execution schema | Task lifecycle, checkpoints, dependency graph, holds. | 2026-09-12 | 2026-09-14 |  | T01 | FS | No | Canonical Task State Machine (CTS) | High | Not Started | 0%
T05 | P2 · Data Plane & Storage | Provision Central Enterprise DB (CDB) relational tables & vector stores | Relational + JSONB + vector namespaces + telemetry. | 2026-09-14 | 2026-09-16 |  | T04 | FS | No | Central Enterprise Database (CDB) | Medium | Not Started | 0%
T06 | P2 · Data Plane & Storage | Connect Headless CMS content models & staging layout schemas | Staged page models, schemas, catalog diffs. | 2026-09-14 | 2026-09-16 |  | T04 | FS | No | Headless CMS & Web Store (CMS) | Medium | Not Started | 0%
T07 | P2 · Data Plane & Storage | Instantiate Institutional Memory Store (MEM) for brand heuristics | Promoted knowledge, brand books, learned heuristics. | 2026-09-14 | 2026-09-16 |  | T04 | FS | No | Institutional Memory Store (MEM) | Medium | Not Started | 0%
T08 | P2 · Data Plane & Storage | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | Content-addressable deliverables by UUID/SHA-256. | 2026-09-16 | 2026-09-18 |  | T05 | FS | No | Artifact & Evidence Registry (ART) | Medium | Not Started | 0%
T09 | P2 · Data Plane & Storage | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | Read/write capability facades to all stores. | 2026-09-16 | 2026-09-18 |  | T05, T06, T07 | FS | No | Governed MCP Data Boundary | High | Not Started | 0%
T10 | P2 · Data Plane & Storage | Configure Agentic RAG Controller with tenant isolation & freshness gates | Model-A exclusive broker; hybrid search + provenance. | 2026-09-18 | 2026-09-19 |  | T03, T09 | FS | No | Agentic RAG Controller | High | Not Started | 0% |  | Model A enforced
T11 | P3 · Sandbox & Sub-Agents | Deploy agent_sandbox with cgroups, seccomp & tmpfs isolation | Micro-virtualization and process isolation. | 2026-09-18 | 2026-09-20 |  | T03 | FS | No | Sandbox Controller (agent_sandbox) | High | Not Started | 0%
T12 | P3 · Sandbox & Sub-Agents | Configure sandbox network proxy with egress allowlisting (DENY_ALL) | Default-deny egress with domain whitelist proxy. | 2026-09-20 | 2026-09-21 |  | T11 | FS | No | Sandbox Controller (agent_sandbox) | High | Not Started | 0%
T13 | P3 · Sandbox & Sub-Agents | Implement sandbox execution audit interception to W3C PROV ledger | Syscall/execution logging to immutable audit. | 2026-09-21 | 2026-09-22 |  | T11, T12 | FS | No | Sandbox Controller & W3C PROV Audit | Medium | Not Started | 0%
T14 | P3 · Sandbox & Sub-Agents | Instantiate specialist sub-agent micro-tools (S_CODE→S_ATTR) in sandbox | Containerize all ephemeral micro-tools. | 2026-09-21 | 2026-09-23 |  | T11, T12 | FS | No | Specialist Sub-Agents (L4_SUBS) | Medium | Not Started | 0%
T15 | P4 · Domain Intelligence & Assets | Configure Intelligence Engine context assembly & brand persona layer | Dynamic context assembly + persona. | 2026-09-23 | 2026-09-24 |  | T04, T10 | FS | No | Intelligence Engine (IE) | High | Not Started | 0%
T16 | P4 · Domain Intelligence & Assets | Ingest & verify product formulations & compliance dossiers (W_PROD) | Evidence dossiers, claim mapping, regulatory lint. | 2026-09-24 | 2026-09-26 |  | T10, T14, T15 | FS | No | Product / Evidence Engine & S_VAL | Medium | Not Started | 0%
T17 | P4 · Domain Intelligence & Assets | Ingest & parse customer support tickets & review sentiment (W_VOICE) | Sentiment, objections, CX clustering. | 2026-09-24 | 2026-09-26 |  | T10, T14, T15 | FS | No | Customer Voice Engine & S_PARSE | Medium | Not Started | 0%
T18 | P4 · Domain Intelligence & Assets | Scrape competitor ad libraries, pricing & market positioning (W_COMP) | Ad libraries, price trajectories, trends. | 2026-09-24 | 2026-09-26 |  | T12, T14, T15 | FS | No | Competitor Intel Engine & S_SCRAPE | Medium | Not Started | 0%
T19 | P4 · Domain Intelligence & Assets | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | Media mix, funnels, budget plans. | 2026-09-26 | 2026-09-29 |  | T16, T17, T18 | FS | No | Strategy Engine & S_ALLOC | High | Not Started | 0%
T20 | P4 · Domain Intelligence & Assets | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | Copy variants, hooks, social calendars. | 2026-09-29 | 2026-10-02 |  | T16, T19 | FS | No | Creative & Content Engine & S_COPY | Medium | Not Started | 0%
T21 | P4 · Domain Intelligence & Assets | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | UI components, schemas, validated diffs. | 2026-09-26 | 2026-10-02 |  | T06, T14, T15 | FS | No | Development Engine & S_CODE | High | Not Started | 0%
T22 | P5 · HITL Clearance | Consolidate worker evidence envelopes & verify confidence intervals | Merge findings, confidence, artifact UUIDs. | 2026-10-02 | 2026-10-04 |  | T19, T20, T21 | FS | No | Intelligence Engine (IE) | High | Not Started | 0%
T23 | P5 · HITL Clearance | Generate structured action previews (spend, code diffs, claims, copy) | HITL-ready previews. | 2026-10-04 | 2026-10-05 |  | T22 | FS | No | Intelligence Engine (IE) | High | Not Started | 0%
T24 | P5 · HITL Clearance | Execute Human-in-the-Loop (HITL) quality, legal & deploy sign-off | Mandatory human approval gate. | 2026-10-05 | 2026-10-06 |  | T23 | FS | No | Human-in-the-Loop (HITL) Gate | High | Not Started | 0%
T25 | P6 · Outbound Actuation & Go-Live | Initialize Outbound Actuation MCP Boundary with audience tokens | Signed dispatch, rate limiting. | 2026-10-06 | 2026-10-07 |  | T24 | FS | No | Outbound Actuation MCP Boundary | High | Not Started | 0% |  | [MISSING] API credentials
T26 | P6 · Outbound Actuation & Go-Live | Deploy live schemas, catalog updates & layout code to Website & CMS | Staged-to-live production push. | 2026-10-07 | 2026-10-09 |  | T25 | FS | No | Outbound MCP & Website / CMS | High | Not Started | 0%
T27 | P6 · Outbound Actuation & Go-Live | Publish ad campaigns & bid targets to Paid Ad Platforms | Meta/Google/TikTok campaigns. | 2026-10-07 | 2026-10-09 |  | T25 | FS | No | Outbound MCP & Paid Ad Platforms | High | Not Started | 0%
T28 | P6 · Outbound Actuation & Go-Live | Publish scheduled social media posts & assets to Social Channels | Scheduled content broadcast. | 2026-10-07 | 2026-10-09 |  | T25 | FS | No | Outbound MCP & Social Channels | High | Not Started | 0%
T29 | P6 · Outbound Actuation & Go-Live | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | Webhook listeners + event consumers. | 2026-10-09 | 2026-10-10 |  | T26, T27, T28 | FS | No | Omnichannel Telemetry Engine | Medium | Not Started | 0%
T30 | P7 · Telemetry & Closeout | Ingest live store traffic, checkout transactions & conversion logs into CDB | Timeseries telemetry ingestion. | 2026-10-10 | 2026-10-11 |  | T29 | FS | No | Telemetry Engine & Central Database | Medium | Not Started | 0%
T31 | P7 · Telemetry & Closeout | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | Attribution + decay scoring. | 2026-10-11 | 2026-10-13 |  | T30 | FS | No | Learning Engine & S_ATTR | Medium | Not Started | 0%
T32 | P7 · Telemetry & Closeout | Promote validated memory deltas into Institutional Memory & IE | Closed-loop learning promotion. | 2026-10-13 | 2026-10-14 |  | T31 | FS | No | Learning Engine, Memory Store & IE | Medium | Not Started | 0%
T33 | P7 · Telemetry & Closeout | Validate end-to-end W3C PROV audit lineage, state integrity & logs | Seal tamper-evident audit trail. | 2026-10-13 | 2026-10-14 |  | T30, T31 | FS | No | W3C PROV Immutable Ledger | High | Not Started | 0%
T34 | P7 · Telemetry & Closeout | Perform final project verification against acceptance criteria & close | Final acceptance + closeout. | 2026-10-14 | 2026-10-14 |  | T32, T33 | FS | No | Intelligence Engine & Brand Owner | High | Not Started | 0%
M1 | P1 · Governance & Policy | M1 · Governance, Policy & Canonical State Initialization | Milestone checkpoint | 2026-09-14 | 2026-09-14 |  | T03, T04 | FS | Yes | Brand Stakeholder / Portfolio Owner | High | Not Started | 0% |  | Milestone
M2 | P2 · Data Plane & Storage | M2 · Governed Data Plane & Central Storage Integration (Model A) | Milestone checkpoint | 2026-09-19 | 2026-09-19 |  | T10 | FS | Yes | Agentic RAG Controller | High | Not Started | 0% |  | Milestone
M3 | P3 · Sandbox & Sub-Agents | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Milestone checkpoint | 2026-09-23 | 2026-09-23 |  | T14 | FS | Yes | Sandbox Controller (agent_sandbox) | High | Not Started | 0% |  | Milestone
M4 | P4 · Domain Intelligence & Assets | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Milestone checkpoint | 2026-10-02 | 2026-10-02 |  | T20, T21 | FS | Yes | Intelligence Engine (IE) | High | Not Started | 0% |  | Milestone
M5 | P5 · HITL Clearance | M5 · HITL Gateway Clearance & Cryptographic Authorization | Milestone checkpoint | 2026-10-06 | 2026-10-06 |  | T24 | FS | Yes | Human-in-the-Loop (HITL) Gate | High | Not Started | 0% |  | Milestone
M6 | P6 · Outbound Actuation & Go-Live | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Milestone checkpoint | 2026-10-10 | 2026-10-10 |  | T29 | FS | Yes | Outbound Actuation MCP Boundary | High | Not Started | 0% |  | Milestone
M7 | P7 · Telemetry & Closeout | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Milestone checkpoint | 2026-10-14 | 2026-10-14 |  | T34 | FS | Yes | Intelligence Engine & Brand Owner | High | Not Started | 0% |  | Milestone

## Gantt
|  | September 2026 | [19 empty] | October 2026
|  | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
ID | Task / Phase
| Legend: | 2026-09-12: Completed; 2026-09-15: Remaining / planned; 2026-09-18: Delayed; 2026-09-21: On Hold; 2026-09-24: Milestone ◆; 2026-09-27: Weekend; 2026-09-30: Today

## Calc (hidden)
Status | Tasks | Phase | Avg Progress % | Milestone Status | Count
Completed |  | P1 · Governance & Policy |  | Completed
In Progress |  | P2 · Data Plane & Storage |  | Remaining
Not Started |  | P3 · Sandbox & Sub-Agents
On Hold |  | P4 · Domain Intelligence & Assets
Delayed |  | P5 · HITL Clearance
P6 · Outbound Actuation & Go-Live
P7 · Telemetry & Closeout

## Dashboard
Governed Multi-Brand Agentic System — Project Dashboard
| Total Tasks | Completed | In Progress | Not Started | Delayed | On Hold | Overall Progress | Total Milestones | Milestones Done | Milestones Left | Days Remaining
Next upcoming tasks
Upcoming milestones
Approaching end date (≤7 days)
Delayed / schedule-conflicted

## Resources
Resource | Total Assigned | Completed | In Progress | Not Started | Remaining | Avg Progress | Notes
No
Yes

## Assumptions & Gaps
Label | Source field / item | Issue | Resolution used | User action needed
[CONFLICT] | flowchart.drawio.html | HTML contains only placeholder 'Untitled Diagram-Page-3'; no diagram data despite MD claiming identical export. | Used Final-Level Full Architecture.md as sole structural source. | Re-export Draw.io diagram if visual reference needed.
[INFERRED] | All task dates | Source has no calendar dates; 34 tasks dated from dependency DAG. | Mapped into 2026-09-11 → 2026-10-14; all within window. | Confirm dates against real calendar.
[INFERRED] | Progress values | Source progress marked [INFERRED] (100/50/25/0%). | All Progress % initialized to 0% per workbook rule for fresh tracking. | Enter actual progress if project is underway.
[INFERRED] | Dependency types | Source lists all dependencies as Finish-to-Start. | All set to FS. | Change to SS/FF/SF if intended.
[INFERRED] | Priority | Not specified in source. | Assigned by gating/criticality (deploy, HITL, foundations = High). | Adjust as needed.
[INFERRED] | Milestone status | Source milestone status marked [INFERRED]. | Milestones start Not Started / 0%. | Mark complete when achieved.
[MISSING] | Platform API credentials | Meta/Google/TikTok/CMS OAuth secrets absent. | Assumed injected via secure vault at T25. | Provide credentials before go-live.
[MISSING] | Budget figures | Spend caps conceptual only; no numeric values. | No numeric budget modeled. | Supply budget caps from Brand Stakeholder.
[DEPENDENCY ISSUE] | DAG validation | Checked for cycles / invalid refs / early starts. | PASS — no cycles, all refs valid, FS ordering satisfied. | None.
[OUTSIDE WINDOW] | Date window | Checked all tasks vs 2026-09-11..10-14. | PASS — every task within window. | None.

## Instructions
GOVERNED MULTI-BRAND AGENTIC SYSTEM — WORKBOOK INSTRUCTIONS
1. Edit tasks: Project Tracker sheet. Type directly into Task Name, Description, Predecessor, Resource, Notes.
2. Change dates: edit Start Date / End Date (columns E/F). Duration, Schedule Health, Gantt and Dashboard recalc automatically.
3. Update progress: enter 0%–100% in Progress % (column N). The Gantt bar fills proportionally.
4. Change status: use the Status dropdown. Keep it in sync with progress (0%=Not Started, 1–99%=In Progress, 100%=Completed). On Hold/Delayed are manual and are never overwritten.
5. Assign resources: type the resource name in Resource / Owner (column K). The Resources sheet and dashboard update.
6. Dependencies: list predecessor Task IDs comma-separated (e.g. 'T05, T06'). Pick FS/SS/FF/SF in Dependency Type. The Schedule Health column flags 'Dep. Conflict' if a task starts before its predecessors finish (FS).
7. Add a new task: type in the row immediately below the table — the table, formulas, dropdowns and formatting extend automatically. Add a matching Gantt row by copying the last Gantt row's formulas if you exceed the buffer.
8. Milestones: tasks with Milestone='Yes' show as a purple ◆ on their single date instead of a bar.
9. Gantt updates: bars are formula-driven from the Tracker. Green=completed portion, blue=remaining, red=delayed, orange=on-hold. Weekends are shaded; today's column is amber.
10. Dashboard: all KPIs, charts and 'upcoming work' lists recalc from the Tracker. The 'upcoming work' formulas use Excel 365 dynamic arrays (FILTER/SORT/TAKE).
Notes: grey italic cells are calculated — do not edit. Requires Excel 365/2021 for dashboard array formulas and LET-free Gantt. All progress was initialized to 0% (see Assumptions & Gaps).