## Gantt
Governed Multi-Brand Agentic System — Project Gantt Chart
Project period: Friday, 11 September 2026 — Wednesday, 14 October 2026 ¦ Model A ¦ Execution boundary: agent_sandbox (AIO Sandbox)
Tasks | 34 | Milestones | 7 | Project Days | 34 | Overall Progress | 69.89% | Source Snapshot | M5 — In Progress | Gantt legend: dark bar = completed portion ¦ light bar = remaining portion ¦ ◆ = milestone ¦ slate bar = phase summary ¦ light columns = weekends
Project Schedule | [9 empty] | September 2026 | [19 empty] | October 2026
ID | Type | Task / Activity | Start Date | End Date | Duration | Predecessor | Resource | % Complete | Status | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
[10 empty] | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
| Summary | Governance, Policy & Canonical State Initialization | 2026-09-11 | 2026-09-14 | 4 |  |  | 100% | Complete
T01 | Task | Define enterprise objectives, tenant scopes, and budget boundaries | 2026-09-11 | 2026-09-12 | 2 |  | Brand Stakeholder / Portfolio Owner | 100% | Completed
T02 | Task | Configure machine-readable policy rules, autonomy tiers, and claim limits | 2026-09-11 | 2026-09-12 | 2 |  | Enterprise Policy Engine | 100% | Completed
T03 | Task | Establish Policy & Authorization Boundary (PAB) evaluation rules | 2026-09-12 | 2026-09-14 | 3 | T01, T02 (FS) | Policy & Authorization Boundary (PAB) | 100% | Completed
T04 | Task | Initialize Canonical Task State Machine (CTS) and DAG execution schema | 2026-09-12 | 2026-09-14 | 3 | T01 (FS) | Canonical Task State Machine (CTS) | 100% | Completed
M1 | Milestone | Governance, Policy & Canonical State Initialization | 2026-09-14 | 2026-09-14 | 0 | Linked: T01, T02, T03, T04 |  |  | Complete | bar: 2026-09-14
| Summary | Governed Data Plane & Central Storage Integration (Model A) | 2026-09-14 | 2026-09-19 | 6 |  |  | 100% | Complete
T05 | Task | Provision Central Enterprise Database (CDB) relational tables & vector stores | 2026-09-14 | 2026-09-16 | 3 | T04 (FS) | Central Enterprise Database (CDB) | 100% | Completed
T06 | Task | Connect Headless CMS content models and staging layout schemas | 2026-09-14 | 2026-09-16 | 3 | T04 (FS) | Headless CMS & Web Store (CMS) | 100% | Completed
T07 | Task | Instantiate Institutional Memory Store (MEM) for brand heuristics & rules | 2026-09-14 | 2026-09-16 | 3 | T04 (FS) | Institutional Memory Store (MEM) | 100% | Completed
T08 | Task | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | 2026-09-16 | 2026-09-18 | 3 | T05 (FS) | Artifact & Evidence Registry (ART) | 100% | Completed
T09 | Task | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | 2026-09-16 | 2026-09-18 | 3 | T05, T06, T07 (FS) | Governed MCP Data Boundary | 100% | Completed
T10 | Task | Configure Agentic RAG Controller with tenant isolation & freshness gates | 2026-09-18 | 2026-09-19 | 2 | T03, T09 (FS) | Agentic RAG Controller | 100% | Completed
M2 | Milestone | Governed Data Plane & Central Storage Integration (Model A) | 2026-09-19 | 2026-09-19 | 0 | Linked: T05, T06, T07, T08, T09, T10 |  |  | Complete | bar: 2026-09-19
| Summary | Sandbox Isolation & Specialist Sub-Agent Readiness | 2026-09-18 | 2026-09-23 | 6 |  |  | 100% | Complete
T11 | Task | Deploy agent_sandbox with cgroups, seccomp, and tmpfs isolation | 2026-09-18 | 2026-09-20 | 3 | T03 (FS) | Sandbox Controller (agent_sandbox) | 100% | Completed
T12 | Task | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL) | 2026-09-20 | 2026-09-21 | 2 | T11 (FS) | Sandbox Controller (agent_sandbox) | 100% | Completed
T13 | Task | Implement sandbox execution audit interception to W3C PROV ledger | 2026-09-21 | 2026-09-22 | 2 | T11, T12 (FS) | Sandbox Controller & W3C PROV Audit | 100% | Completed
T14 | Task | Instantiate specialist sub-agent micro-tools (S_CODE to S_ATTR) in sandbox | 2026-09-21 | 2026-09-23 | 3 | T11, T12 (FS) | Specialist Sub-Agents (L4_SUBS) | 100% | Completed
M3 | Milestone | Sandbox Isolation & Specialist Sub-Agent Readiness | 2026-09-23 | 2026-09-23 | 0 | Linked: T11, T12, T13, T14 |  |  | Complete | bar: 2026-09-23
| Summary | Domain Intelligence Ingestion & Asset Synthesis Complete | 2026-09-23 | 2026-10-02 | 10 |  |  | 100% | Complete
T15 | Task | Configure Intelligence Engine context assembly & brand persona layer | 2026-09-23 | 2026-09-24 | 2 | T04, T10 (FS) | Intelligence Engine (IE) | 100% | Completed
T16 | Task | Ingest & verify product formulations and compliance dossiers (W_PROD) | 2026-09-24 | 2026-09-26 | 3 | T10, T14, T15 (FS) | Product / Evidence Engine & S_VAL | 100% | Completed
T17 | Task | Ingest & parse customer support tickets and review sentiment (W_VOICE) | 2026-09-24 | 2026-09-26 | 3 | T10, T14, T15 (FS) | Customer Voice Engine & S_PARSE | 100% | Completed
T18 | Task | Scrape competitor ad libraries, pricing, and market positioning (W_COMP) | 2026-09-24 | 2026-09-26 | 3 | T12, T14, T15 (FS) | Competitor Intel Engine & S_SCRAPE | 100% | Completed
T19 | Task | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | 2026-09-26 | 2026-09-29 | 4 | T16, T17, T18 (FS) | Strategy Engine & S_ALLOC | 100% | Completed
T20 | Task | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | 2026-09-29 | 2026-10-02 | 4 | T16, T19 (FS) | Creative & Content Engine & S_COPY | 100% | Completed
T21 | Task | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | 2026-09-26 | 2026-10-02 | 7 | T06, T14, T15 (FS) | Development Engine & S_CODE | 100% | Completed
M4 | Milestone | Domain Intelligence Ingestion & Asset Synthesis Complete | 2026-10-02 | 2026-10-02 | 0 | Linked: T15, T16, T17, T18, T19, T20, T21 |  |  | Complete | bar: 2026-10-02
| Summary | HITL Gateway Clearance & Cryptographic Authorization | 2026-10-02 | 2026-10-06 | 5 |  |  | 28.57% | In Progress
T22 | Task | Consolidate worker evidence envelopes & verify confidence intervals | 2026-10-02 | 2026-10-04 | 3 | T19, T20, T21 (FS) | Intelligence Engine (IE) | 50% | In Progress
T23 | Task | Generate structured action previews (spend, code diffs, claims, copy) | 2026-10-04 | 2026-10-05 | 2 | T22 (FS) | Intelligence Engine (IE) | 25% | In Progress
T24 | Task | Execute Human-in-the-Loop (HITL) quality, legal, and deploy sign-off | 2026-10-05 | 2026-10-06 | 2 | T23 (FS) | Human-in-the-Loop (HITL) Gate | 0% | Not Started
M5 | Milestone | HITL Gateway Clearance & Cryptographic Authorization | 2026-10-06 | 2026-10-06 | 0 | Linked: T22, T23, T24 |  |  | In Progress | bar: 2026-10-06
| Summary | Outbound Actuation, Telemetry & Omnichannel Go-Live | 2026-10-06 | 2026-10-10 | 5 |  |  | 0% | Planned
T25 | Task | Initialize Outbound Actuation MCP Boundary with audience tokens | 2026-10-06 | 2026-10-07 | 2 | T24 (FS) | Outbound Actuation MCP Boundary | 0% | Not Started
T26 | Task | Deploy live schemas, catalog updates & layout code to Website & CMS | 2026-10-07 | 2026-10-09 | 3 | T25 (FS) | Outbound MCP & Website / CMS | 0% | Not Started
T27 | Task | Publish ad campaigns and bid targets to Paid Ad Platforms | 2026-10-07 | 2026-10-09 | 3 | T25 (FS) | Outbound MCP & Paid Ad Platforms | 0% | Not Started
T28 | Task | Publish scheduled social media posts and assets to Social Channels | 2026-10-07 | 2026-10-09 | 3 | T25 (FS) | Outbound MCP & Social Channels | 0% | Not Started
T29 | Task | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | 2026-10-09 | 2026-10-10 | 2 | T26, T27, T28 (FS) | Omnichannel Telemetry Engine | 0% | Not Started
M6 | Milestone | Outbound Actuation, Telemetry & Omnichannel Go-Live | 2026-10-10 | 2026-10-10 | 0 | Linked: T25, T26, T27, T28, T29 |  |  | Planned | bar: 2026-10-10
| Summary | Closed-Loop Telemetry Optimization & Final Project Closeout | 2026-10-10 | 2026-10-14 | 5 |  |  | 0% | Planned
T30 | Task | Ingest live store traffic, checkout transactions & conversion logs into CDB | 2026-10-10 | 2026-10-11 | 2 | T29 (FS) | Telemetry Engine & Central Database | 0% | Not Started
T31 | Task | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | 2026-10-11 | 2026-10-13 | 3 | T30 (FS) | Learning Engine & S_ATTR | 0% | Not Started
T32 | Task | Promote validated memory deltas into Institutional Memory and IE | 2026-10-13 | 2026-10-14 | 2 | T31 (FS) | Learning Engine, Memory Store & IE | 0% | Not Started
T33 | Task | Validate end-to-end W3C PROV audit lineage, state integrity & logs | 2026-10-13 | 2026-10-14 | 2 | T30, T31 (FS) | W3C PROV Immutable Ledger | 0% | Not Started
T34 | Task | Perform final project verification against acceptance criteria & close | 2026-10-14 | 2026-10-14 | 1 | T32, T33 (FS) | Intelligence Engine & Brand Owner | 0% | Not Started
M7 | Milestone | Closed-Loop Telemetry Optimization & Final Project Closeout | 2026-10-14 | 2026-10-14 | 0 | Linked: T30, T31, T32, T33, T34 |  |  | Planned | bar: 2026-10-14
Formulas:
Start Date = MIN([Start Date, row below]:D11)
End Date = MAX([End Date, row below]:E11)

## Source Notes
Source Item | Source-Derived Detail
Project Window | 2026-09-11 to 2026-10-14 (34 calendar days)
Access-Control Model | Model A — Intelligence Engine is the exclusive broker for Agentic RAG/data plane
Execution Boundary | agent_sandbox (AIO Sandbox) hosts ephemeral sub-agents and micro-tools
Task Count | 34 tasks (T01–T34)
Milestone Count | 7 milestones (M1–M7)
Dependency Type | Finish-to-Start (FS) relationships as specified in the project plan
Calendar Standard | Durations use inclusive calendar days, including weekends
Date Basis | The source project plan explicitly labels task dates as [INFERRED] from the architecture/DAG
Progress Basis | The source project plan explicitly labels progress percentages as [INFERRED]
Status Logic in Gantt | Task Status is formula-derived from the source % Complete: 100%=Completed, 1–99%=In Progress, 0%=Not Started
Summary Rows | Derived from each source milestone group; dates and weighted progress update automatically from linked task rows
Milestone Rows | Dates, linked tasks and source statuses are preserved from the source milestone table
Architecture Cross-Check | Component/resource names were checked against Final-Level Full Architecture.md
Flowchart Cross-Check | The project plan reports no conflict between the Markdown architecture and the Draw.io HTML export
FS Display | Task predecessor IDs are labeled (FS), matching the source dependency-detail table. Source dates use same-day boundary handoffs where successor start equals predecessor end.
Milestone % Complete | Left blank because the source milestone table provides status but no numeric milestone completion percentage.