## Project Tracker
Governed Multi-Brand Agentic System — Project Tracker
Project Start | 2026-09-11 | Project End | 2026-10-14 | Calendar Days | 34 | Governance Model | Model A | Execution Boundary | agent_sandbox (AIO Sandbox) | [7 empty] | T02
Editable inputs are highlighted pale yellow. Formula-driven columns are shaded blue-gray. Progress begins at 0%; Status auto-reconciles until you manually override a row (e.g., On Hold or Delayed).
Task ID | Phase | Task Name | Description | Deliverable / Output | Start Date | End Date | Duration | Predecessor | Dependency Type | Milestone | Resource / Owner | Priority | Status | Progress % | Schedule Health | Notes |  | Pred1 | Pred2 | Pred3 | Pred4 | Pred5 | Pred6 | Pred7 | Pred Count | Valid Count | Self Cycle | Max Pred Start | Max Pred End | Conflict | Upcoming Task Key | Milestone Key | Approaching Key | Attention Key
T01 | M1 · Governance, Policy & Canonical State Initialization | Define enterprise objectives, tenant scopes, and budget boundaries | High strategic responsibility; inputs business goals at kickoff and accepts final delivery at project close. | [INFERRED] Approved enterprise objectives, tenant scopes, and budget boundaries | 2026-09-11 | 2026-09-12 | 2 |  |  | No | Brand Stakeholder / Portfolio Owner |  | Not Started | 0% | On Track | [9 empty] | 0 | 0 | FALSE | 0 | 0 | FALSE | 46276.0001 |  | 46277.0001 |  | 1 |  | 1
T02 | M1 · Governance, Policy & Canonical State Initialization | Configure machine-readable policy rules, autonomy tiers, and claim limits | Automated policy rule definition; defines risk matrices and compliance envelopes. | [INFERRED] Versioned policy rules, autonomy tiers, and claim limits | 2026-09-11 | 2026-09-12 | 2 |  |  | No | Enterprise Policy Engine |  | Not Started | 0% | On Track | [9 empty] | 0 | 0 | FALSE | 0 | 0 | FALSE | 46276.0001 |  | 46277.0001 |  | 2 |  | 2
T03 | M1 · Governance, Policy & Canonical State Initialization | Establish Policy & Authorization Boundary (PAB) evaluation rules | Strategic intent & policy rules must exist before PAB can enforce bounds. | [INFERRED] PAB evaluation and authorization rule set | 2026-09-12 | 2026-09-14 | 3 | T01, T02 | FS | No | Policy & Authorization Boundary (PAB) |  | Not Started | 0% | On Track |  |  | Pred1: T01; Pred2: T02 | 2 | 2 | FALSE | 2026-09-11 | 2026-09-12 | FALSE | 46277.0001 |  |  |  | 3
T04 | M1 · Governance, Policy & Canonical State Initialization | Initialize Canonical Task State Machine (CTS) and DAG execution schema | Scope and budgets are prerequisites for Canonical Task State DAG initialization. | [INFERRED] Canonical task lifecycle and DAG execution schema | 2026-09-12 | 2026-09-14 | 3 | T01 | FS | No | Canonical Task State Machine (CTS) |  | Not Started | 0% | On Track |  |  | Pred1: T01 | 1 | 1 | FALSE | 2026-09-11 | 2026-09-12 | FALSE | 46277.0001 |  |  |  | 4
M1 | M1 · Governance, Policy & Canonical State Initialization | Governance, Policy & Canonical State Initialization | Explicit checkpoint linked to T01, T02, T03, T04. | Governance, Policy & Canonical State Initialization | 2026-09-14 | 2026-09-14 | 1 | T01, T02, T03, T04 | FS | Yes | Unassigned |  | Not Started | 0% | On Track | [INFERRED] Milestone linkage is represented as FS predecessors from the source-listed linked tasks; source milestone status was inferred and is reset to 0%/Not Started per workbook requirement. |  | Pred1: T01; Pred2: T02; Pred3: T03; Pred4: T04 | 4 | 4 | FALSE | 2026-09-12 | 2026-09-14 | FALSE |  | 46279.0001 |  |  |  | 1
T05 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Provision Central Enterprise Database (CDB) relational tables & vector stores | State ledger schemas must precede database tables, CMS models, and memory namespaces. | [INFERRED] Provisioned relational, vector, and telemetry-ready central data stores | 2026-09-14 | 2026-09-16 | 3 | T04 | FS | No | Central Enterprise Database (CDB) |  | Not Started | 0% | On Track |  |  | Pred1: T04 | 1 | 1 | FALSE | 2026-09-12 | 2026-09-14 | FALSE | 46279.0001 |  |  |  | 5
T06 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Connect Headless CMS content models and staging layout schemas | State ledger schemas must precede database tables, CMS models, and memory namespaces. | [INFERRED] Connected CMS content models and staging layout schemas | 2026-09-14 | 2026-09-16 | 3 | T04 | FS | No | Headless CMS & Web Store (CMS) |  | Not Started | 0% | On Track |  |  | Pred1: T04 | 1 | 1 | FALSE | 2026-09-12 | 2026-09-14 | FALSE | 46279.0001 |  |  |  | 6
T07 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Instantiate Institutional Memory Store (MEM) for brand heuristics & rules | State ledger schemas must precede database tables, CMS models, and memory namespaces. | [INFERRED] Institutional memory namespaces for brand heuristics and rules | 2026-09-14 | 2026-09-16 | 3 | T04 | FS | No | Institutional Memory Store (MEM) |  | Not Started | 0% | On Track |  |  | Pred1: T04 | 1 | 1 | FALSE | 2026-09-12 | 2026-09-14 | FALSE | 46279.0001 |  |  |  | 7
T08 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | Immutable blob storage; stores deliverables, code diffs, and evidence dossiers by UUID/SHA-256. | [INFERRED] UUID/hash-based artifact and evidence registry configuration | 2026-09-16 | 2026-09-18 | 3 | T05 | FS | No | Artifact & Evidence Registry (ART) |  | Not Started | 0% | On Track | [INFERRED] Dependency type defaults to FS because the source lists predecessor T05 but omits T08 from the dependency-type detail table. |  | Pred1: T05 | 1 | 1 | FALSE | 2026-09-14 | 2026-09-16 | FALSE | 46281.0001 |  |  |  | 8
T09 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | Physical data stores must be provisioned before MCP Data Gateway establishes CRUD adapters. | [INFERRED] Governed CRUD gateways and database connection pools | 2026-09-16 | 2026-09-18 | 3 | T05, T06, T07 | FS | No | Governed MCP Data Boundary |  | Not Started | 0% | On Track |  |  | Pred1: T05; Pred2: T06; Pred3: T07 | 3 | 3 | FALSE | 2026-09-14 | 2026-09-16 | FALSE | 46281.0002 |  |  |  | 9
T10 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Configure Agentic RAG Controller with tenant isolation & freshness gates | PAB access rules and MCP data connectors are required to configure Agentic RAG Controller. | [INFERRED] Tenant-isolated Agentic RAG controller with freshness/provenance gates | 2026-09-18 | 2026-09-19 | 2 | T03, T09 | FS | No | Agentic RAG Controller |  | Not Started | 0% | On Track |  |  | Pred1: T03; Pred2: T09 | 2 | 2 | FALSE | 2026-09-16 | 2026-09-18 | FALSE | 46283.0002 |  |  |  | 10
M2 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Governed Data Plane & Central Storage Integration (Model A) | Explicit checkpoint linked to T05, T06, T07, T08, T09, T10. | Governed Data Plane & Central Storage Integration (Model A) | 2026-09-19 | 2026-09-19 | 1 | T05, T06, T07, T08, T09, T10 | FS | Yes | Unassigned |  | Not Started | 0% | On Track | [INFERRED] Milestone linkage is represented as FS predecessors from the source-listed linked tasks; source milestone status was inferred and is reset to 0%/Not Started per workbook requirement. |  | T05 | T06 | T07 | T08 | T09 | T10 |  | 6 | 6 | FALSE | 2026-09-18 | 2026-09-19 | FALSE |  | 46284.0002 |  |  |  | 2
T11 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Deploy agent_sandbox with cgroups, seccomp, and tmpfs isolation | Security policies dictate sandbox cgroup and seccomp profile definitions. | [INFERRED] Isolated agent_sandbox runtime with cgroups, seccomp, and tmpfs controls | 2026-09-18 | 2026-09-20 | 3 | T03 | FS | No | Sandbox Controller (agent_sandbox) |  | Not Started | 0% | On Track |  |  | T03 T05: T03 |  | 1 | 1 | FALSE | 2026-09-12 | 2026-09-14 | FALSE | 46283.0002 |  |  |  | 11
T12 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL) | Isolated execution environment; enforces cgroups, seccomp filters, tmpfs shredding, and network proxying. | [INFERRED] DENY_ALL egress policy with approved network proxy allowlist | 2026-09-20 | 2026-09-21 | 2 | T11 | FS | No | Sandbox Controller (agent_sandbox) |  | Not Started | 0% | On Track | [INFERRED] Dependency type defaults to FS because the source lists predecessor T11 but omits T12 from the dependency-type detail table. |  | T03 T05: T11 |  | 1 | 1 | FALSE | 2026-09-18 | 2026-09-20 | FALSE | 46285.0002 |  |  |  | 12
T13 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Implement sandbox execution audit interception to W3C PROV ledger | Sandbox virtualization and egress proxy must be active before sub-agents and audit hooks launch. | [INFERRED] Sandbox execution audit stream into the W3C PROV ledger | 2026-09-21 | 2026-09-22 | 2 | T11, T12 | FS | No | Sandbox Controller & W3C PROV Audit |  | Not Started | 0% | On Track |  |  | T03 T05: T11; T09 T06: T12 |  | 2 | 2 | FALSE | 2026-09-20 | 2026-09-21 | FALSE | 46286.0002 |  |  |  | 13
T14 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Instantiate specialist sub-agent micro-tools (S_CODE to S_ATTR) in sandbox | Sandbox virtualization and egress proxy must be active before sub-agents and audit hooks launch. | [INFERRED] Containerized specialist sub-agent micro-tools S_CODE through S_ATTR | 2026-09-21 | 2026-09-23 | 3 | T11, T12 | FS | No | Specialist Sub-Agents (L4_SUBS) |  | Not Started | 0% | On Track |  |  | T03 T05: T11; T09 T06: T12 |  | 2 | 2 | FALSE | 2026-09-20 | 2026-09-21 | FALSE | 46286.0002 |  |  |  | 14
M3 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Sandbox Isolation & Specialist Sub-Agent Readiness | Explicit checkpoint linked to T11, T12, T13, T14. | Sandbox Isolation & Specialist Sub-Agent Readiness | 2026-09-23 | 2026-09-23 | 1 | T11, T12, T13, T14 | FS | Yes | Unassigned |  | Not Started | 0% | On Track | [INFERRED] Milestone linkage is represented as FS predecessors from the source-listed linked tasks; source milestone status was inferred and is reset to 0%/Not Started per workbook requirement. |  | T11 | T12 | T13 | T14 |  |  |  | 4 | 4 | FALSE | 2026-09-21 | 2026-09-23 | FALSE |  | 46288.0002 |  |  |  | 3
T15 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Configure Intelligence Engine context assembly & brand persona layer | Task state schema and RAG access must be active before IE context assembly can operate. | [INFERRED] Intelligence Engine context assembly and brand persona layer | 2026-09-23 | 2026-09-24 | 2 | T04, T10 | FS | No | Intelligence Engine (IE) |  | Not Started | 0% | On Track |  |  | T03 T05: T04; T09 T06: T10 |  | 2 | 2 | FALSE | 2026-09-18 | 2026-09-19 | FALSE | 46288.0002 |  |  |  | 15
T16 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Ingest & verify product formulations and compliance dossiers (W_PROD) | Workers require RAG data access, sandbox micro-tools, and IE context grants to ingest domain intel. | [INFERRED] Verified claims/compliance dossier and product specification evidence | 2026-09-24 | 2026-09-26 | 3 | T10, T14, T15 | FS | No | Product / Evidence Engine & S_VAL |  | Not Started | 0% | On Track |  |  | T03 T05: T10; T09 T06: T14; T09 T07: T15 |  | 3 | 3 | FALSE | 2026-09-23 | 2026-09-24 | FALSE | 46289.0002 |  |  |  | 16
T17 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Ingest & parse customer support tickets and review sentiment (W_VOICE) | Workers require RAG data access, sandbox micro-tools, and IE context grants to ingest domain intel. | [INFERRED] Parsed customer sentiment vectors and objection profiles | 2026-09-24 | 2026-09-26 | 3 | T10, T14, T15 | FS | No | Customer Voice Engine & S_PARSE |  | Not Started | 0% | On Track |  |  | T03 T05: T10; T09 T06: T14; T09 T07: T15 |  | 3 | 3 | FALSE | 2026-09-23 | 2026-09-24 | FALSE | 46289.0003 |  |  |  | 17
T18 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Scrape competitor ad libraries, pricing, and market positioning (W_COMP) | Ephemeral micro-tool workers (S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE, S_ATTR). | [INFERRED] Competitor pricing, ad-library, and market-positioning intelligence | 2026-09-24 | 2026-09-26 | 3 | T12, T14, T15 | FS | No | Competitor Intel Engine & S_SCRAPE |  | Not Started | 0% | On Track | [CONFLICT] Task table/direct listing: T12, T14, T15. Detailed dependency table: T10, T14, T15. Workbook preserves T12, T14, T15. |  | T03 T05: T12; T09 T06: T14; T09 T07: T15 |  | 3 | 3 | FALSE | 2026-09-23 | 2026-09-24 | FALSE | 46289.0003 |  |  |  | 18
T19 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | Omnichannel marketing strategy requires verified claims, customer voice, and competitor intel. | [INFERRED] Omnichannel roadmap, funnel, and budget allocation plan | 2026-09-26 | 2026-09-29 | 4 | T16, T17, T18 | FS | No | Strategy Engine & S_ALLOC |  | Not Started | 0% | On Track |  |  | T03 T05: T16; T09 T06: T17; T09 T07: T18 |  | 3 | 3 | FALSE | 2026-09-24 | 2026-09-26 | FALSE | 46291.0003 |  |  |  | 19
T20 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | Creative copy and visual briefs depend on approved claims and strategic channel allocations. | [INFERRED] Multi-channel copy variants, hooks, visual briefs, and social content | 2026-09-29 | 2026-10-02 | 4 | T16, T19 | FS | No | Creative & Content Engine & S_COPY |  | Not Started | 0% | On Track |  |  | T03 T05: T16; T09 T06: T19 |  | 2 | 2 | FALSE | 2026-09-26 | 2026-09-29 | FALSE | 46294.0003 |  |  |  | 21
T21 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | Website development requires CMS staging models, AST coder tools, and IE directives. | [INFERRED] Responsive UI templates, CMS schemas, and validated code diffs | 2026-09-26 | 2026-10-02 | 7 | T06, T14, T15 | FS | No | Development Engine & S_CODE |  | Not Started | 0% | On Track |  |  | T03 T05: T06; T09 T06: T14; T09 T07: T15 |  | 3 | 3 | FALSE | 2026-09-23 | 2026-09-24 | FALSE | 46291.0003 |  |  |  | 20
M4 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Domain Intelligence Ingestion & Asset Synthesis Complete | Explicit checkpoint linked to T15, T16, T17, T18, T19, T20, T21. | Domain Intelligence Ingestion & Asset Synthesis Complete | 2026-10-02 | 2026-10-02 | 1 | T15, T16, T17, T18, T19, T20, T21 | FS | Yes | Unassigned |  | Not Started | 0% | On Track | [INFERRED] Milestone linkage is represented as FS predecessors from the source-listed linked tasks; source milestone status was inferred and is reset to 0%/Not Started per workbook requirement. |  | T15 | T16 | T17 | T18 | T19 | T20 | T21 | 7 | 7 | FALSE | 2026-09-29 | 2026-10-02 | FALSE |  | 46297.0003 |  |  |  | 4
T22 | M5 · HITL Gateway Clearance & Cryptographic Authorization | Consolidate worker evidence envelopes & verify confidence intervals | Strategy plans, creative assets, and code diffs must be compiled into evidence envelopes. | [INFERRED] Consolidated evidence envelopes with confidence verification | 2026-10-02 | 2026-10-04 | 3 | T19, T20, T21 | FS | No | Intelligence Engine (IE) |  | Not Started | 0% | On Track |  |  | T15: T19; T16: T20; T17: T21; 7: 3; 7: 3 | FALSE | 2026-09-29 | 2026-10-02 | FALSE | 46297.0003 |  |  |  | 22
T23 | M5 · HITL Gateway Clearance & Cryptographic Authorization | Generate structured action previews (spend, code diffs, claims, copy) | Validated evidence envelopes are required to format structured action previews. | [INFERRED] Structured action previews for spend, code, claims, and copy | 2026-10-04 | 2026-10-05 | 2 | T22 | FS | No | Intelligence Engine (IE) |  | Not Started | 0% | On Track |  |  | T15: T22; 7: 1; 7: 1 | FALSE | 2026-10-02 | 2026-10-04 | FALSE | 46299.0003 |  |  |  | 23
T24 | M5 · HITL Gateway Clearance & Cryptographic Authorization | Execute Human-in-the-Loop (HITL) quality, legal, and deploy sign-off | Action previews are the mandatory input for the Human-in-the-Loop approval gate. | [INFERRED] HITL approval/rejection decision with signed authorization evidence | 2026-10-05 | 2026-10-06 | 2 | T23 | FS | No | Human-in-the-Loop (HITL) Gate |  | Not Started | 0% | On Track |  |  | T15: T23; 7: 1; 7: 1 | FALSE | 2026-10-04 | 2026-10-05 | FALSE | 46300.0003 |  |  |  | 24
M5 | M5 · HITL Gateway Clearance & Cryptographic Authorization | HITL Gateway Clearance & Cryptographic Authorization | Explicit checkpoint linked to T22, T23, T24. | HITL Gateway Clearance & Cryptographic Authorization | 2026-10-06 | 2026-10-06 | 1 | T22, T23, T24 | FS | Yes | Unassigned |  | Not Started | 0% | On Track | [INFERRED] Milestone linkage is represented as FS predecessors from the source-listed linked tasks; source milestone status was inferred and is reset to 0%/Not Started per workbook requirement. |  | T15: T22; T16: T23; T17: T24; 7: 3; 7: 3 | FALSE | 2026-10-05 | 2026-10-06 | FALSE |  | 46301.0004 |  |  |  | 5
T25 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Initialize Outbound Actuation MCP Boundary with audience tokens | Signed cryptographic HITL approval grants release execution directives to Outbound MCP. | [INFERRED] Authenticated outbound actuation MCP boundary and audience-token controls | 2026-10-06 | 2026-10-07 | 2 | T24 | FS | No | Outbound Actuation MCP Boundary |  | Not Started | 0% | On Track |  |  | T15: T24; 7: 1; 7: 1 | FALSE | 2026-10-05 | 2026-10-06 | FALSE | 46301.0004 |  |  |  | 25
T26 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Deploy live schemas, catalog updates & layout code to Website & CMS | Outbound MCP gateway must be authenticated before dispatching web code, ads, and social posts. | [INFERRED] Live website/CMS schemas, catalog updates, and layout code deployment | 2026-10-07 | 2026-10-09 | 3 | T25 | FS | No | Outbound MCP & Website / CMS |  | Not Started | 0% | On Track |  |  | T15: T25; 7: 1; 7: 1 | FALSE | 2026-10-06 | 2026-10-07 | FALSE | 46302.0004 |  |  |  | 26
T27 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Publish ad campaigns and bid targets to Paid Ad Platforms | Outbound MCP gateway must be authenticated before dispatching web code, ads, and social posts. | [INFERRED] Published paid-media campaigns and bid targets | 2026-10-07 | 2026-10-09 | 3 | T25 | FS | No | Outbound MCP & Paid Ad Platforms |  | Not Started | 0% | On Track |  |  | T15: T25; 7: 1; 7: 1 | FALSE | 2026-10-06 | 2026-10-07 | FALSE | 46302.0004 |  |  |  | 27
T28 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Publish scheduled social media posts and assets to Social Channels | Outbound MCP gateway must be authenticated before dispatching web code, ads, and social posts. | [INFERRED] Published scheduled social posts and media assets | 2026-10-07 | 2026-10-09 | 3 | T25 | FS | No | Outbound MCP & Social Channels |  | Not Started | 0% | On Track |  |  | T15: T25; 7: 1; 7: 1 | FALSE | 2026-10-06 | 2026-10-07 | FALSE | 46302.0004 |  |  |  | 28
T29 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | External surfaces must be active before Omnichannel Telemetry Engine webhooks can attach. | [INFERRED] Connected telemetry webhooks, pixel events, and server-log feeds | 2026-10-09 | 2026-10-10 | 2 | T26, T27, T28 | FS | No | Omnichannel Telemetry Engine |  | Not Started | 0% | On Track |  |  | T15: T26; T16: T27; T17: T28; 7: 3; 7: 3 | FALSE | 2026-10-07 | 2026-10-09 | FALSE | 46304.0004 |  |  |  | 29
M6 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Outbound Actuation, Telemetry & Omnichannel Go-Live | Explicit checkpoint linked to T25, T26, T27, T28, T29. | Outbound Actuation, Telemetry & Omnichannel Go-Live | 2026-10-10 | 2026-10-10 | 1 | T25, T26, T27, T28, T29 | FS | Yes | Unassigned |  | Not Started | 0% | On Track | [INFERRED] Milestone linkage is represented as FS predecessors from the source-listed linked tasks; source milestone status was inferred and is reset to 0%/Not Started per workbook requirement. |  | T25 | T26 | T27 | T28 | T29 |  |  | 5 | 5 | FALSE | 2026-10-09 | 2026-10-10 | FALSE |  | 46305.0004 |  |  |  | 6
T30 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Ingest live store traffic, checkout transactions & conversion logs into CDB | Telemetry listeners must be online to ingest live traffic, conversions, and transaction records. | [INFERRED] Ingested store traffic, checkout, transaction, and conversion telemetry | 2026-10-10 | 2026-10-11 | 2 | T29 | FS | No | Telemetry Engine & Central Database |  | Not Started | 0% | On Track |  |  | T15: T29; 7: 1; 7: 1 | FALSE | 2026-10-09 | 2026-10-10 | FALSE | 46305.0004 |  |  |  | 30
T31 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | Attribution and creative decay algorithms require live performance metrics from Central DB. | [INFERRED] Attribution weights, creative-decay metrics, and ROAS calculations | 2026-10-11 | 2026-10-13 | 3 | T30 | FS | No | Learning Engine & S_ATTR |  | Not Started | 0% | On Track |  |  | T15: T30; 7: 1; 7: 1 | FALSE | 2026-10-10 | 2026-10-11 | FALSE | 46306.0004 |  |  |  | 31
T32 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Promote validated memory deltas into Institutional Memory and IE | Attribution weights must be validated before promotion into Institutional Memory. | [INFERRED] Validated learning/memory deltas promoted to Memory Store and IE | 2026-10-13 | 2026-10-14 | 2 | T31 | FS | No | Learning Engine, Memory Store & IE |  | Not Started | 0% | On Track |  |  | T15: T31; 7: 1; 7: 1 | FALSE | 2026-10-11 | 2026-10-13 | FALSE | 46308.0004 |  |  |  | 32
T33 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Validate end-to-end W3C PROV audit lineage, state integrity & logs | Complete execution and telemetry logs must be sealed in W3C PROV audit registry. | [INFERRED] Verified end-to-end W3C PROV audit lineage and state integrity | 2026-10-13 | 2026-10-14 | 2 | T30, T31 | FS | No | W3C PROV Immutable Ledger |  | Not Started | 0% | On Track |  |  | T15: T30; T16: T31; 7: 2; 7: 2 | FALSE | 2026-10-11 | 2026-10-13 | FALSE | 46308.0004 |  |  |  | 33
T34 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Perform final project verification against acceptance criteria & close | Final project acceptance occurs only after closed-loop learning and audit integrity verification. | [INFERRED] Final acceptance verification and project closeout record | 2026-10-14 | 2026-10-14 | 1 | T32, T33 | FS | No | Intelligence Engine & Brand Owner |  | Not Started | 0% | On Track |  |  | T15: T32; T16: T33; 7: 2; 7: 2 | FALSE | 2026-10-13 | 2026-10-14 | FALSE | 46309.0005 |  |  |  | 34
M7 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Closed-Loop Telemetry Optimization & Final Project Closeout | Explicit checkpoint linked to T30, T31, T32, T33, T34. | Closed-Loop Telemetry Optimization & Final Project Closeout | 2026-10-14 | 2026-10-14 | 1 | T30, T31, T32, T33, T34 | FS | Yes | Unassigned |  | Not Started | 0% | On Track | [INFERRED] Milestone linkage is represented as FS predecessors from the source-listed linked tasks; source milestone status was inferred and is reset to 0%/Not Started per workbook requirement. |  | T30 | T31 | T32 | T33 | T34 |  |  | 5 | 5 | FALSE | 2026-10-14 | 2026-10-14 | FALSE |  | 46309.0005 |  |  |  | 7
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
[27 empty] | FALSE | 0 | 0 | FALSE
Formulas:
Upcoming Task Key = IF(AND([Task ID]<>"",[Milestone]="No",[Status]<>"Completed",[Start Date]>=TODAY()),[Start Date]+ROW()/100000,"")
Milestone Key = IF(AND([Task ID]<>"",[Milestone]="Yes",[Status]<>"Completed",[Start Date]>=TODAY()),[Start Date]+ROW()/100000,"")
Approaching Key = IF(AND([Task ID]<>"",[Milestone]="No",[Status]<>"Completed",[End Date]>=TODAY(),[End Date]<=TODAY()+3),[End Date]+ROW()/100000,"")

## Gantt
Dynamic Gantt — 2026-09-11 to 2026-10-14 | [6 empty] | SEP 2026 | [19 empty] | OCT 2026
Green = completed portion · Blue = In Progress · Gray = Not Started · Red = Delayed · Amber = On Hold · ◆ = Milestone | [6 empty] | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
Task ID | Phase | Task Name | Status | Progress % | Schedule Health | Milestone | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
T01 | M1 · Governance, Policy & Canonical State Initialization | Define enterprise objectives, tenant scopes, and budget boundaries | Not Started | 0% | On Track | No
T02 | M1 · Governance, Policy & Canonical State Initialization | Configure machine-readable policy rules, autonomy tiers, and claim limits | Not Started | 0% | On Track | No
T03 | M1 · Governance, Policy & Canonical State Initialization | Establish Policy & Authorization Boundary (PAB) evaluation rules | Not Started | 0% | On Track | No
T04 | M1 · Governance, Policy & Canonical State Initialization | Initialize Canonical Task State Machine (CTS) and DAG execution schema | Not Started | 0% | On Track | No
M1 | M1 · Governance, Policy & Canonical State Initialization | Governance, Policy & Canonical State Initialization | Not Started | 0% | On Track | Yes | bar: 2026-09-14
T05 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Provision Central Enterprise Database (CDB) relational tables & vector stores | Not Started | 0% | On Track | No
T06 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Connect Headless CMS content models and staging layout schemas | Not Started | 0% | On Track | No
T07 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Instantiate Institutional Memory Store (MEM) for brand heuristics & rules | Not Started | 0% | On Track | No
T08 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | Not Started | 0% | On Track | No
T09 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | Not Started | 0% | On Track | No
T10 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Configure Agentic RAG Controller with tenant isolation & freshness gates | Not Started | 0% | On Track | No
M2 | M2 · Governed Data Plane & Central Storage Integration (Model A) | Governed Data Plane & Central Storage Integration (Model A) | Not Started | 0% | On Track | Yes | bar: 2026-09-19
T11 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Deploy agent_sandbox with cgroups, seccomp, and tmpfs isolation | Not Started | 0% | On Track | No
T12 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL) | Not Started | 0% | On Track | No
T13 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Implement sandbox execution audit interception to W3C PROV ledger | Not Started | 0% | On Track | No
T14 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Instantiate specialist sub-agent micro-tools (S_CODE to S_ATTR) in sandbox | Not Started | 0% | On Track | No
M3 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | Sandbox Isolation & Specialist Sub-Agent Readiness | Not Started | 0% | On Track | Yes | bar: 2026-09-23
T15 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Configure Intelligence Engine context assembly & brand persona layer | Not Started | 0% | On Track | No
T16 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Ingest & verify product formulations and compliance dossiers (W_PROD) | Not Started | 0% | On Track | No
T17 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Ingest & parse customer support tickets and review sentiment (W_VOICE) | Not Started | 0% | On Track | No
T18 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Scrape competitor ad libraries, pricing, and market positioning (W_COMP) | Not Started | 0% | On Track | No
T19 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | Not Started | 0% | On Track | No
T20 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | Not Started | 0% | On Track | No
T21 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | Not Started | 0% | On Track | No
M4 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | Domain Intelligence Ingestion & Asset Synthesis Complete | Not Started | 0% | On Track | Yes | bar: 2026-10-02
T22 | M5 · HITL Gateway Clearance & Cryptographic Authorization | Consolidate worker evidence envelopes & verify confidence intervals | Not Started | 0% | On Track | No
T23 | M5 · HITL Gateway Clearance & Cryptographic Authorization | Generate structured action previews (spend, code diffs, claims, copy) | Not Started | 0% | On Track | No
T24 | M5 · HITL Gateway Clearance & Cryptographic Authorization | Execute Human-in-the-Loop (HITL) quality, legal, and deploy sign-off | Not Started | 0% | On Track | No
M5 | M5 · HITL Gateway Clearance & Cryptographic Authorization | HITL Gateway Clearance & Cryptographic Authorization | Not Started | 0% | On Track | Yes | bar: 2026-10-06
T25 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Initialize Outbound Actuation MCP Boundary with audience tokens | Not Started | 0% | On Track | No
T26 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Deploy live schemas, catalog updates & layout code to Website & CMS | Not Started | 0% | On Track | No
T27 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Publish ad campaigns and bid targets to Paid Ad Platforms | Not Started | 0% | On Track | No
T28 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Publish scheduled social media posts and assets to Social Channels | Not Started | 0% | On Track | No
T29 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | Not Started | 0% | On Track | No
M6 | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | Outbound Actuation, Telemetry & Omnichannel Go-Live | Not Started | 0% | On Track | Yes | bar: 2026-10-10
T30 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Ingest live store traffic, checkout transactions & conversion logs into CDB | Not Started | 0% | On Track | No
T31 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | Not Started | 0% | On Track | No
T32 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Promote validated memory deltas into Institutional Memory and IE | Not Started | 0% | On Track | No
T33 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Validate end-to-end W3C PROV audit lineage, state integrity & logs | Not Started | 0% | On Track | No
T34 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Perform final project verification against acceptance criteria & close | Not Started | 0% | On Track | No
M7 | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | Closed-Loop Telemetry Optimization & Final Project Closeout | Not Started | 0% | On Track | Yes | bar: 2026-10-14

## Dashboard
Project Management Dashboard
[12 empty] | Status | Task Count | Phase | Average Progress | Resource / Owner | Assigned Tasks | Milestone State | Count
Total Tasks |  | Completed Tasks |  | In-Progress Tasks |  | Not Started Tasks |  | Delayed Tasks |  |  |  | Not Started | 34 | M1 · Governance, Policy & Canonical State Initialization | 0% | Intelligence Engine (IE) | 3 | Completed | 0
34 |  | 0 |  | 0 |  | 34 |  | 0 |  |  |  | In Progress | 0 | M2 · Governed Data Plane & Central Storage Integration (Model A) | 0% | Sandbox Controller (agent_sandbox) | 2 | Remaining | 7
[12 empty] | Completed | 0 | M3 · Sandbox Isolation & Specialist Sub-Agent Readiness | 0% | Agentic RAG Controller | 1
[12 empty] | On Hold | 0 | M4 · Domain Intelligence Ingestion & Asset Synthesis Complete | 0% | Artifact & Evidence Registry (ART) | 1
Overall Progress % |  | Total Milestones |  | Completed Milestones |  | Remaining Milestones |  | Project Days Remaining |  |  |  | Delayed | 0 | M5 · HITL Gateway Clearance & Cryptographic Authorization | 0% | Brand Stakeholder / Portfolio Owner | 1
0% |  | 7 |  | 0 |  | 7 |  | 34 | [5 empty] | M6 · Outbound Actuation, Telemetry & Omnichannel Go-Live | 0% | Canonical Task State Machine (CTS) | 1
[14 empty] | M7 · Closed-Loop Telemetry Optimization & Final Project Closeout | 0% | Central Enterprise Database (CDB) | 1
[16 empty] | Competitor Intel Engine & S_SCRAPE | 1
[16 empty] | Creative & Content Engine & S_COPY | 1
[16 empty] | Customer Voice Engine & S_PARSE | 1
Upcoming & Attention Queue
Next Upcoming Tasks |  |  | Upcoming Milestones |  |  | Approaching End Date (3 days) |  |  | Delayed / Schedule-Conflicted
Date | ID | Task / Milestone | Date | ID | Task / Milestone | End Date | ID | Task | End Date | ID | Task
2026-09-11 | T01 | Define enterprise objectives, tenant scopes, and budget boundaries | 2026-09-14 | M1 | Governance, Policy & Canonical State Initialization | 2026-09-12 | T01 | Define enterprise objectives, tenant scopes, and budget boundaries
2026-09-11 | T02 | Configure machine-readable policy rules, autonomy tiers, and claim limits | 2026-09-19 | M2 | Governed Data Plane & Central Storage Integration (Model A) | 2026-09-12 | T02 | Configure machine-readable policy rules, autonomy tiers, and claim limits
2026-09-12 | T03 | Establish Policy & Authorization Boundary (PAB) evaluation rules | 2026-09-23 | M3 | Sandbox Isolation & Specialist Sub-Agent Readiness
2026-09-12 | T04 | Initialize Canonical Task State Machine (CTS) and DAG execution schema | 2026-10-02 | M4 | Domain Intelligence Ingestion & Asset Synthesis Complete
2026-09-14 | T05 | Provision Central Enterprise Database (CDB) relational tables & vector stores | 2026-10-06 | M5 | HITL Gateway Clearance & Cryptographic Authorization

## Resources
Resource Summary & Workload Overlap
Assignment counts and average progress are formula-driven from Project Tracker. Overlap flags do not assume capacity limits.
Resource | Total Assigned Tasks | Completed | In Progress | Remaining | Average Progress | Notes | Overlap Indicator | Source Assigned Tasks
Intelligence Engine (IE) | 3 | 0 | 0 | 3 | 0% | Task-schedule assignment for T15, T22, T23; supporting component roles are detailed in the source architecture. | Potential overlap detected (T22 / T23, 2026-10-04 to 2026-10-04); no capacity limit is defined in the source. | T15, T22, T23
Sandbox Controller (agent_sandbox) | 2 | 0 | 0 | 2 | 0% | Isolated execution environment; enforces cgroups, seccomp filters, tmpfs shredding, and network proxying. | Potential overlap detected (T11 / T12, 2026-09-20 to 2026-09-20); no capacity limit is defined in the source. | T11, T12
Agentic RAG Controller | 1 | 0 | 0 | 1 | 0% | Sole authorized data broker for Intelligence Engine under Model A; manages hybrid vector search and freshness. |  | T10
Artifact & Evidence Registry (ART) | 1 | 0 | 0 | 1 | 0% | Immutable blob storage; stores deliverables, code diffs, and evidence dossiers by UUID/SHA-256. |  | T08
Brand Stakeholder / Portfolio Owner | 1 | 0 | 0 | 1 | 0% | High strategic responsibility; inputs business goals at kickoff and accepts final delivery at project close. |  | T01
Canonical Task State Machine (CTS) | 1 | 0 | 0 | 1 | 0% | Central state tracking engine; manages DAG transitions, task holds, checkpoints, and dependency locks. |  | T04
Central Enterprise Database (CDB) | 1 | 0 | 0 | 1 | 0% | Primary system of record for operational tables, vector namespaces, and telemetry time-series. |  | T05
Competitor Intel Engine & S_SCRAPE | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T18; supporting component roles are detailed in the source architecture. |  | T18
Creative & Content Engine & S_COPY | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T20; supporting component roles are detailed in the source architecture. |  | T20
Customer Voice Engine & S_PARSE | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T17; supporting component roles are detailed in the source architecture. |  | T17
Development Engine & S_CODE | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T21; supporting component roles are detailed in the source architecture. |  | T21
Enterprise Policy Engine | 1 | 0 | 0 | 1 | 0% | Automated policy rule definition; defines risk matrices and compliance envelopes. |  | T02
Governed MCP Data Boundary | 1 | 0 | 0 | 1 | 0% | Database gateway; exposes read/write CRUD capability facades under strict schema validation. |  | T09
Headless CMS & Web Store (CMS) | 1 | 0 | 0 | 1 | 0% | Digital asset and page model store; handles staged layout schemas and live storefront content. |  | T06
Human-in-the-Loop (HITL) Gate | 1 | 0 | 0 | 1 | 0% | Mandatory human sign-off; reviews action previews for spend, legal compliance, and code deployment. |  | T24
Institutional Memory Store (MEM) | 1 | 0 | 0 | 1 | 0% | Long-term knowledge base; stores promoted heuristics, brand voice rules, and model deltas. |  | T07
Intelligence Engine & Brand Owner | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T34; supporting component roles are detailed in the source architecture. |  | T34
Learning Engine & S_ATTR | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T31; supporting component roles are detailed in the source architecture. |  | T31
Learning Engine, Memory Store & IE | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T32; supporting component roles are detailed in the source architecture. |  | T32
Omnichannel Telemetry Engine | 1 | 0 | 0 | 1 | 0% | Real-time event ingestor; aggregates conversion webhooks, pixel events, and server logs. |  | T29
Outbound Actuation MCP Boundary | 1 | 0 | 0 | 1 | 0% | Security egress perimeter; validates audience tokens and dispatches signed API calls to external surfaces. |  | T25
Outbound MCP & Paid Ad Platforms | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T27; supporting component roles are detailed in the source architecture. |  | T27
Outbound MCP & Social Channels | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T28; supporting component roles are detailed in the source architecture. |  | T28
Outbound MCP & Website / CMS | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T26; supporting component roles are detailed in the source architecture. |  | T26
Policy & Authorization Boundary (PAB) | 1 | 0 | 0 | 1 | 0% | Core security gate; evaluates caller identity, token validity, and monotonic attenuation per invocation. |  | T03
Product / Evidence Engine & S_VAL | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T16; supporting component roles are detailed in the source architecture. |  | T16
Sandbox Controller & W3C PROV Audit | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T13; supporting component roles are detailed in the source architecture. |  | T13
Specialist Sub-Agents (L4_SUBS) | 1 | 0 | 0 | 1 | 0% | Ephemeral micro-tool workers (S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE, S_ATTR). |  | T14
Strategy Engine & S_ALLOC | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T19; supporting component roles are detailed in the source architecture. |  | T19
Telemetry Engine & Central Database | 1 | 0 | 0 | 1 | 0% | Task-schedule assignment for T30; supporting component roles are detailed in the source architecture. |  | T30
W3C PROV Immutable Ledger | 1 | 0 | 0 | 1 | 0% | Audit authority; records tamper-evident entity-activity-agent relationships and cryptographic signatures. |  | T33

## Assumptions & Gaps
Assumptions & Gaps Register
Label | Source Field / Item | Issue | Resolution Used in Workbook | User Action Needed
[INFERRED] | Schedule dates (T01–T34) | The project-plan Markdown explicitly states that calendar dates were inferred from architecture/DAG constraints. | Preserved the supplied 2026-09-11 to 2026-10-14 dates as editable Excel dates. | Review/adjust dates if implementation reality differs.
[INFERRED] | Dependency type — T08 | T08 depends on T05, but T08 is omitted from the detailed dependency-type table. | Used FS, per the workbook rule for unspecified dependency types. | Confirm another dependency type if intended.
[INFERRED] | Dependency type — T12 | T12 depends on T11, but T12 is omitted from the detailed dependency-type table. | Used FS, per the workbook rule for unspecified dependency types. | Confirm another dependency type if intended.
[CONFLICT] | T18 predecessor | Task table and direct dependency list say T12, T14, T15; dependency-detail table says T10, T14, T15. | Preserved T12, T14, T15 because it appears in both the task table and direct listing. Conflict is also noted on T18. | Confirm whether T12 or T10 is the intended predecessor.
[CONFLICT] | Initial progress/status | Source plan contains inferred progress/status values (including completed work), while workbook requirements explicitly require 0% initially. | Reset every task and milestone to 0%; Status defaults to Not Started and auto-reconciles from Progress %. | Enter actual progress when available.
[MISSING] | Priority | No High/Medium/Low task priorities are specified in the sources. | Priority cells are intentionally blank with a dropdown. | Assign priorities if needed.
[MISSING] | Platform credentials | Source notes say production API/OAuth credentials are omitted. | No credential data was invented or stored in the workbook. | Provide credentials only through the intended secure vault/process.
[MISSING] | Budget figures | Budget boundaries/spend controls are referenced, but no numeric amounts are provided. | No budget values were invented. | Add approved figures in the project system when available.

## Instructions
Workbook Instructions
# | Action | How to Use | Important Note
1 | Edit tasks | Use Project Tracker. Pale-yellow cells are intended for task inputs; blue-gray Duration and Schedule Health cells are calculated. | Keep Task IDs unique.
2 | Change dates | Edit Start Date and End Date in Project Tracker using real Excel dates. | Duration, health checks, Gantt bars, upcoming work, and dashboard metrics update automatically.
3 | Update Progress % | Enter any value from 0% to 100% in Progress %. | 0% defaults to Not Started, 1–99% to In Progress, 100% to Completed.
4 | Change Status | Status is formula-driven by default. You may manually choose On Hold or Delayed (or another status) from the dropdown. | A manual choice replaces the row's auto-status formula. To restore automation, copy the Status formula from a neighboring auto-status row.
5 | Assign resources | Edit Resource / Owner. Use exact resource names from the Resources sheet when possible; multiple resources may be separated with semicolons. | Resource counts use text matching and update from the tracker.
6 | Modify dependencies | Enter predecessor Task ID(s) separated by commas and choose FS, SS, FF, or SF. | Schedule Health checks missing IDs, direct self-cycles, invalid dates, project-window violations, and date conflicts. The source DAG was separately validated as acyclic at build time.
7 | Add a new task safely | Insert a new row inside the Project Tracker Excel Table, give it a unique Task ID, dates, milestone flag, and any predecessor IDs. | Table formulas/validation should extend automatically. The Gantt is pre-wired for up to 100 tracker rows.
8 | Milestone markers | Milestone rows use Milestone = Yes and Start Date = End Date. | They appear as ◆ on the Gantt and are counted separately from normal tasks on the Dashboard.
9 | Gantt behavior | The Gantt reads directly from Project Tracker and redraws bars by date/status/progress via formulas and conditional formatting. | Weekends are differentiated; progress overlays the completed portion of each duration bar.
10 | Dashboard indicators | Use KPI cards, charts, and the Upcoming & Attention Queue for management review. | Project Days Remaining uses TODAY(); delayed/conflicted queues update from tracker status and Schedule Health.