## Project Tracker
Governed Multi-Brand Agentic System
11 Sep–14 Oct 2026. Provisional compressed schedule. Review Assumptions & Gaps before committing resources.
Blue text = editable. Gray cells = formulas. 34 activities + 7 milestones. Blank table rows are reserved for growth.
Task ID | Phase | Task Name | Description | Start Date | End Date | Duration | Predecessor | Dependency Type | Milestone | Resource / Owner | Priority | Status | Progress % | Schedule Health | Notes | Effective status | ID issue | Date issue | Predecessor count | Predecessor 1 | Predecessor 2 | Predecessor 3 | Predecessor 4 | Predecessor 5 | Predecessor 6 | Predecessor 7 | Predecessor 8 | Predecessor position 1 | Predecessor position 2 | Predecessor position 3 | Predecessor position 4 | Predecessor position 5 | Predecessor position 6 | Predecessor position 7 | Predecessor position 8 | Missing references | Timing issues | Cycle issue | Unique phase | Upcoming key | Milestone key | Due soon key | Conflict key | Resource tokens
T01 | Governance & state | Define enterprise objectives, tenant scopes, and budget boundaries | Agree objectives, tenant boundaries, budget caps and risk appetite. | 2026-09-11 | 2026-09-11 | 1 |  |  | No | Brand Stakeholder / Portfolio Owner |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-11 to 2026-09-12, 2d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 1d. Original resource/tools: Brand Stakeholder / Portfolio Owner. | Not Started |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 46276.0007 | 1000000000 | 46276.0007 | 1000000000 | ;Brand Stakeholder / Portfolio Owner; | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T02 | Governance & state | Configure machine-readable policy rules, autonomy tiers, and claim limits | Version policy envelopes, autonomy tiers and permitted claims. | 2026-09-11 | 2026-09-11 | 1 |  |  | No | Enterprise Policy Engine |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-11 to 2026-09-12, 2d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 1d. Original resource/tools: Enterprise Policy Engine. | Not Started |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46276.0008 | 1000000000 | 46276.0008 | 1000000000 | ;Enterprise Policy Engine; | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T03 | Governance & state | Establish Policy & Authorization Boundary (PAB) evaluation rules | Validate identity, delegated tokens, tenant scope and risk tier. | 2026-09-12 | 2026-09-13 | 2 | T01,T02 | FS | No | Policy & Authorization Boundary (PAB) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-12 to 2026-09-14, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Policy & Authorization Boundary (PAB). | Not Started |  |  | 2 | T01 | T02 | [6 empty] | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46277.0009 | 1000000000 | 46278.0009 | 1000000000 | ;Policy & Authorization Boundary (PAB); | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T04 | Governance & state | Initialize Canonical Task State Machine (CTS) and DAG execution schema | Define lifecycle states, checkpoints, dependency locks and holds. | 2026-09-12 | 2026-09-13 | 2 | T01 | FS | No | Canonical Task State Machine (CTS) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-12 to 2026-09-14, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Canonical Task State Machine (CTS). | Not Started |  |  | 1 | T01 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46277.001 | 1000000000 | 46278.001 | 1000000000 | ;Canonical Task State Machine (CTS); | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
M1 | Governance & state | Governance, Policy & Canonical State Initialization | Explicit project checkpoint. Mark complete only after linked work is accepted. | 2026-09-14 | 2026-09-14 | 0 | T01,T02,T03,T04 | FF | Yes | Unassigned |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §3. Source checkpoint date retained (source labels all dates [INFERRED]). [INFERRED] FF link permits completion-day checkpoint. Owner missing. | Not Started |  |  | 4 | T01 | T02 | T03 | T04 |  |  |  |  | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 46279.0011 | 1000000000 | 1000000000 | ;Unassigned; | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T05 | Data & storage | Provision Central Enterprise Database (CDB) relational tables & vector stores | Create relational/JSONB records, vector namespaces, state and telemetry stores. | 2026-09-14 | 2026-09-15 | 2 | T04 | FS | No | Central Enterprise Database (CDB) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-14 to 2026-09-16, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Central Enterprise Database (CDB). | Not Started |  |  | 1 | T04 | [7 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 46279.0012 | 1000000000 | 46280.0012 | 1000000000 | ;Central Enterprise Database (CDB); | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T06 | Data & storage | Connect Headless CMS content models and staging layout schemas | Define staged page models, catalog objects, layouts and assets. | 2026-09-14 | 2026-09-15 | 2 | T04 | FS | No | Headless CMS & Web Store (CMS) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-14 to 2026-09-16, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Headless CMS & Web Store (CMS). | Not Started |  |  | 1 | T04 | [7 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46279.0013 | 1000000000 | 46280.0013 | 1000000000 | ;Headless CMS & Web Store (CMS); | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T07 | Data & storage | Instantiate Institutional Memory Store (MEM) for brand heuristics & rules | Store brand books, heuristics and promoted learning deltas. | 2026-09-14 | 2026-09-15 | 2 | T04 | FS | No | Institutional Memory Store (MEM) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-14 to 2026-09-16, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Institutional Memory Store (MEM). | Not Started |  |  | 1 | T04 | [7 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46279.0014 | 1000000000 | 46280.0014 | 1000000000 | ;Institutional Memory Store (MEM); | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T08 | Data & storage | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | Address evidence, copy packs and code diffs by UUID / SHA-256. | 2026-09-16 | 2026-09-18 | 3 | T05 | FS | No | Artifact & Evidence Registry (ART) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-16 to 2026-09-18, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. [INFERRED] FS type. Original resource/tools: Artifact & Evidence Registry (ART). | Not Started |  |  | 1 | T05 | [7 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46281.0015 | 1000000000 | 1000000000 | 1000000000 | ;Artifact & Evidence Registry (ART); | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T09 | Data & storage | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | Connect governed CRUD adapters and enforce schemas on all data access. | 2026-09-16 | 2026-09-17 | 2 | T05,T06,T07 | FS | No | Governed MCP Data Boundary |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-16 to 2026-09-18, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Governed MCP Data Boundary. | Not Started |  |  | 3 | T05 | T06 | T07 | [5 empty] | 6 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46281.0016 | 1000000000 | 46282.0016 | 1000000000 | ;Governed MCP Data Boundary; | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T10 | Data & storage | Configure Agentic RAG Controller with tenant isolation & freshness gates | Enforce tenant-scoped retrieval, freshness and provenance through IE. | 2026-09-18 | 2026-09-18 | 1 | T03,T09 | FS | No | Agentic RAG Controller |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-18 to 2026-09-19, 2d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 1d. Original resource/tools: Agentic RAG Controller. | Not Started |  |  | 2 | T03 | T09 | [6 empty] | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46283.0017 | 1000000000 | 1000000000 | 1000000000 | ;Agentic RAG Controller; | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
M2 | Data & storage | Governed Data Plane & Central Storage Integration (Model A) | Explicit project checkpoint. Mark complete only after linked work is accepted. | 2026-09-19 | 2026-09-19 | 0 | T05,T06,T07,T08,T09,T10 | FF | Yes | Unassigned |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §3. Source checkpoint date retained (source labels all dates [INFERRED]). [INFERRED] FF link permits completion-day checkpoint. Owner missing. | Not Started |  |  | 6 | T05 | T06 | T07 | T08 | T09 | T10 |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 46284.0018 | 1000000000 | 1000000000 | ;Unassigned; | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T11 | Sandbox & tools | Deploy agent_sandbox with cgroups, seccomp, and tmpfs isolation | Isolate processes and memory, scrub tmpfs on teardown. | 2026-09-14 | 2026-09-15 | 2 | T03 | FS | No | Sandbox Controller (agent_sandbox) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-18 to 2026-09-20, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Sandbox Controller (agent_sandbox). | Not Started |  |  | 1 | T03 | [7 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 46279.0019 | 1000000000 | 46280.0019 | 1000000000 | ;Sandbox Controller (agent_sandbox); | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T12 | Sandbox & tools | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL) | Deny egress by default. Use approved proxy domains for external scraping. | 2026-09-16 | 2026-09-17 | 2 | T11 | FS | No | Sandbox Controller (agent_sandbox) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-20 to 2026-09-21, 2d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. [INFERRED] FS type. Original resource/tools: Sandbox Controller (agent_sandbox). | Not Started |  |  | 1 | T11 | [7 empty] | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46281.002 | 1000000000 | 46282.002 | 1000000000 | ;Sandbox Controller (agent_sandbox); | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T13 | Sandbox & tools | Implement sandbox execution audit interception to W3C PROV ledger | Stream command, exit-code, memory and error events to immutable audit. | 2026-09-18 | 2026-09-19 | 2 | T11,T12 | FS | No | Sandbox Controller (agent_sandbox);W3C PROV Immutable Ledger |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-21 to 2026-09-22, 2d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: Sandbox Controller & W3C PROV Audit. | Not Started |  |  | 2 | T11 | T12 | [6 empty] | 13 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46283.0021 | 1000000000 | 1000000000 | 1000000000 | ;Sandbox Controller (agent_sandbox);W3C PROV Immutable Ledger; | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T14 | Sandbox & tools | Instantiate specialist sub-agent micro-tools (S_CODE to S_ATTR) in sandbox | Provide S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE and S_ATTR. | 2026-09-18 | 2026-09-19 | 2 | T11,T12 | FS | No | Specialist Sub-Agents (L4_SUBS) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-21 to 2026-09-23, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Specialist Sub-Agents (L4_SUBS). | Not Started |  |  | 2 | T11 | T12 | [6 empty] | 13 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46283.0022 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS); | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
M3 | Sandbox & tools | Sandbox Isolation & Specialist Sub-Agent Readiness | Explicit project checkpoint. Mark complete only after linked work is accepted. | 2026-09-23 | 2026-09-23 | 0 | T11,T12,T13,T14 | FF | Yes | Unassigned |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §3. Source checkpoint date retained (source labels all dates [INFERRED]). [INFERRED] FF link permits completion-day checkpoint. Owner missing. | Not Started |  |  | 4 | T11 | T12 | T13 | T14 |  |  |  |  | 13 | 14 | 15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 46288.0023 | 1000000000 | 1000000000 | ;Unassigned; | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T15 | Intelligence & assets | Configure Intelligence Engine context assembly & brand persona layer | Assemble persona, bounded grants, tools, token budgets and context. | 2026-09-19 | 2026-09-19 | 1 | T04,T10 | FS | No | Intelligence Engine (IE / Orchestrator) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-23 to 2026-09-24, 2d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 1d. Original resource/tools: Intelligence Engine (IE). | Not Started |  |  | 2 | T04 | T10 | [6 empty] | 4 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 46284.0024 | 1000000000 | 1000000000 | 1000000000 | ;Intelligence Engine (IE / Orchestrator); | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T16 | Intelligence & assets | Ingest & verify product formulations and compliance dossiers (W_PROD) | Create verified claims dossiers and product specifications with S_VAL. | 2026-09-20 | 2026-09-21 | 2 | T10,T14,T15 | FS | No | Specialist Sub-Agents (L4_SUBS);Product / Evidence Engine (W_PROD) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-24 to 2026-09-26, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Product / Evidence Engine & S_VAL. | Not Started |  |  | 3 | T10 | T14 | T15 | [5 empty] | 11 | 16 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46285.0025 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS);Product / Evidence Engine (W_PROD); | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T17 | Intelligence & assets | Ingest & parse customer support tickets and review sentiment (W_VOICE) | Produce anonymized sentiment vectors and objection profiles with S_PARSE. | 2026-09-20 | 2026-09-21 | 2 | T10,T14,T15 | FS | No | Specialist Sub-Agents (L4_SUBS);Customer Voice Engine (W_VOICE) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-24 to 2026-09-26, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Customer Voice Engine & S_PARSE. | Not Started |  |  | 3 | T10 | T14 | T15 | [5 empty] | 11 | 16 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46285.0026 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS);Customer Voice Engine (W_VOICE); | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T18 | Intelligence & assets | Scrape competitor ad libraries, pricing, and market positioning (W_COMP) | Collect ad-library trends, competitor pricing and positioning with S_SCRAPE. | 2026-09-20 | 2026-09-21 | 2 | T10,T12,T14,T15 | FS | No | Specialist Sub-Agents (L4_SUBS);Competitor Intel Engine (W_COMP) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-24 to 2026-09-26, 3d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. [CONFLICT] §1/§2.1 vs §2.2 predecessors: union retained. Original resource/tools: Competitor Intel Engine & S_SCRAPE. | Not Started |  |  | 4 | T10 | T12 | T14 | T15 |  |  |  |  | 11 | 14 | 16 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46285.0027 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS);Competitor Intel Engine (W_COMP); | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T19 | Intelligence & assets | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | Prepare roadmaps, funnel models and spend proposals with S_ALLOC. | 2026-09-22 | 2026-09-24 | 3 | T16,T17,T18 | FS | No | Specialist Sub-Agents (L4_SUBS);Strategy Engine (W_STRAT) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-26 to 2026-09-29, 4d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 3d. Original resource/tools: Strategy Engine & S_ALLOC. | Not Started |  |  | 3 | T16 | T17 | T18 | [5 empty] | 19 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46287.0028 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS);Strategy Engine (W_STRAT); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T20 | Intelligence & assets | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | Produce copy variants, hooks, visual briefs and social schedules with S_COPY. | 2026-09-25 | 2026-09-27 | 3 | T16,T19 | FS | No | Specialist Sub-Agents (L4_SUBS);Creative & Content Engine (W_CREAT) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-29 to 2026-10-02, 4d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 3d. Original resource/tools: Creative & Content Engine & S_COPY. | Not Started |  |  | 2 | T16 | T19 | [6 empty] | 19 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46290.0029 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS);Creative & Content Engine (W_CREAT); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T21 | Intelligence & assets | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | Build validated UI templates, CMS schemas and code diffs with S_CODE. | 2026-09-20 | 2026-09-26 | 7 | T06,T14,T15 | FS | No | Specialist Sub-Agents (L4_SUBS);Development Engine (W_DEV) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-09-26 to 2026-10-02, 7d; original progress 100% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: Development Engine & S_CODE. | Not Started |  |  | 3 | T06 | T14 | T15 | [5 empty] | 7 | 16 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46285.003 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS);Development Engine (W_DEV); | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
M4 | Intelligence & assets | Domain Intelligence Ingestion & Asset Synthesis Complete | Explicit project checkpoint. Mark complete only after linked work is accepted. | 2026-10-02 | 2026-10-02 | 0 | T15,T16,T17,T18,T19,T20,T21 | FF | Yes | Unassigned |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §3. Source checkpoint date retained (source labels all dates [INFERRED]). [INFERRED] FF link permits completion-day checkpoint. Owner missing. | Not Started |  |  | 7 | T15 | T16 | T17 | T18 | T19 | T20 | T21 |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 0 | 0 | 0 | 0 |  | 1000000000 | 46297.0031 | 1000000000 | 1000000000 | ;Unassigned; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T22 | Evidence & approval | Consolidate worker evidence envelopes & verify confidence intervals | Verify candidate artifacts, provenance, confidence and proposed state deltas. | 2026-09-28 | 2026-09-29 | 2 | T19,T20,T21 | FS | No | Intelligence Engine (IE / Orchestrator) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-02 to 2026-10-04, 3d; original progress 50% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Intelligence Engine (IE). | Not Started |  |  | 3 | T19 | T20 | T21 | [5 empty] | 22 | 23 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 46293.0032 | 1000000000 | 1000000000 | 1000000000 | ;Intelligence Engine (IE / Orchestrator); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T23 | Evidence & approval | Generate structured action previews (spend, code diffs, claims, copy) | Show spend proposals, claim dossiers, copy and code diffs for review. | 2026-09-30 | 2026-09-30 | 1 | T22 | FS | No | Intelligence Engine (IE / Orchestrator) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-04 to 2026-10-05, 2d; original progress 25% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 1d. Original resource/tools: Intelligence Engine (IE). | Not Started |  |  | 1 | T22 | [7 empty] | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46295.0033 | 1000000000 | 1000000000 | 1000000000 | ;Intelligence Engine (IE / Orchestrator); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T24 | Evidence & approval | Execute Human-in-the-Loop (HITL) quality, legal, and deploy sign-off | Obtain signed spend, legal, quality and deployment clearance. | 2026-10-01 | 2026-10-01 | 1 | T23 | FS | No | Human-in-the-Loop (HITL) Gate |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-05 to 2026-10-06, 2d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 1d. Original resource/tools: Human-in-the-Loop (HITL) Gate. | Not Started |  |  | 1 | T23 | [7 empty] | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46296.0034 | 1000000000 | 1000000000 | 1000000000 | ;Human-in-the-Loop (HITL) Gate; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
M5 | Evidence & approval | HITL Gateway Clearance & Cryptographic Authorization | Explicit project checkpoint. Mark complete only after linked work is accepted. | 2026-10-06 | 2026-10-06 | 0 | T22,T23,T24 | FF | Yes | Unassigned |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §3. Source checkpoint date retained (source labels all dates [INFERRED]). [INFERRED] FF link permits completion-day checkpoint. Owner missing. | Not Started |  |  | 3 | T22 | T23 | T24 | [5 empty] | 26 | 27 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 46301.0035 | 1000000000 | 1000000000 | ;Unassigned; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T25 | Launch & telemetry | Initialize Outbound Actuation MCP Boundary with audience tokens | Authenticate signed dispatch, audience tokens and rate limiting. | 2026-10-02 | 2026-10-03 | 2 | T24 | FS | No | Outbound Actuation MCP Boundary |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-06 to 2026-10-07, 2d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: Outbound Actuation MCP Boundary. | Not Started |  |  | 1 | T24 | [7 empty] | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 46297.0036 | 1000000000 | 1000000000 | 1000000000 | ;Outbound Actuation MCP Boundary; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T26 | Launch & telemetry | Deploy live schemas, catalog updates & layout code to Website & CMS | Release approved storefront/catalog/layout changes through outbound MCP. | 2026-10-04 | 2026-10-05 | 2 | T25 | FS | No | Headless CMS & Web Store (CMS);Outbound Actuation MCP Boundary;Live Website & Headless CMS Surface |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-07 to 2026-10-09, 3d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Outbound MCP & Website / CMS. | Not Started |  |  | 1 | T25 | [7 empty] | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46299.0037 | 1000000000 | 1000000000 | 1000000000 | ;Headless CMS & Web Store (CMS);Outbound Actuation MCP Boundary;Live Website & Headless CMS Surface; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T27 | Launch & telemetry | Publish ad campaigns and bid targets to Paid Ad Platforms | Release approved paid campaigns and bid targets. Confirm platform scope. | 2026-10-04 | 2026-10-05 | 2 | T25 | FS | No | Outbound Actuation MCP Boundary;Paid Ad Platforms (Meta, Google, TikTok) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-07 to 2026-10-09, 3d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Outbound MCP & Paid Ad Platforms. | Not Started |  |  | 1 | T25 | [7 empty] | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46299.0038 | 1000000000 | 1000000000 | 1000000000 | ;Outbound Actuation MCP Boundary;Paid Ad Platforms (Meta, Google, TikTok); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T28 | Launch & telemetry | Publish scheduled social media posts and assets to Social Channels | Release approved media assets, copy and scheduled social posts. | 2026-10-04 | 2026-10-05 | 2 | T25 | FS | No | Outbound Actuation MCP Boundary;Social Channels (Instagram, X, YouTube) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-07 to 2026-10-09, 3d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Outbound MCP & Social Channels. | Not Started |  |  | 1 | T25 | [7 empty] | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46299.0039 | 1000000000 | 1000000000 | 1000000000 | ;Outbound Actuation MCP Boundary;Social Channels (Instagram, X, YouTube); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T29 | Launch & telemetry | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | Attach webhooks, event streams, conversions and error-log collectors. | 2026-10-06 | 2026-10-07 | 2 | T26,T27,T28 | FS | No | Omnichannel Telemetry Engine |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-09 to 2026-10-10, 2d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: Omnichannel Telemetry Engine. | Not Started |  |  | 3 | T26 | T27 | T28 | [5 empty] | 31 | 32 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46301.004 | 1000000000 | 1000000000 | 1000000000 | ;Omnichannel Telemetry Engine; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
M6 | Launch & telemetry | Outbound Actuation, Telemetry & Omnichannel Go-Live | Explicit project checkpoint. Mark complete only after linked work is accepted. | 2026-10-10 | 2026-10-10 | 0 | T25,T26,T27,T28,T29 | FF | Yes | Unassigned |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §3. Source checkpoint date retained (source labels all dates [INFERRED]). [INFERRED] FF link permits completion-day checkpoint. Owner missing. | Not Started |  |  | 5 | T25 | T26 | T27 | T28 | T29 |  |  |  | 30 | 31 | 32 | 33 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 46305.0041 | 1000000000 | 1000000000 | ;Unassigned; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T30 | Learning & closeout | Ingest live store traffic, checkout transactions & conversion logs into CDB | Persist transaction, checkout, traffic and conversion events. | 2026-10-08 | 2026-10-09 | 2 | T29 | FS | No | Central Enterprise Database (CDB);Omnichannel Telemetry Engine |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-10 to 2026-10-11, 2d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: Telemetry Engine & Central Database. | Not Started |  |  | 1 | T29 | [7 empty] | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 46303.0042 | 1000000000 | 1000000000 | 1000000000 | ;Central Enterprise Database (CDB);Omnichannel Telemetry Engine; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T31 | Learning & closeout | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | Estimate attribution weights, creative fatigue and ROAS with S_ATTR. | 2026-10-10 | 2026-10-11 | 2 | T30 | FS | No | Specialist Sub-Agents (L4_SUBS);Learning & Performance Engine (W_LEARN) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-11 to 2026-10-13, 3d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Duration reduced to 2d. Original resource/tools: Learning Engine & S_ATTR. | Not Started |  |  | 1 | T30 | [7 empty] | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46305.0043 | 1000000000 | 1000000000 | 1000000000 | ;Specialist Sub-Agents (L4_SUBS);Learning & Performance Engine (W_LEARN); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T32 | Learning & closeout | Promote validated memory deltas into Institutional Memory and IE | Promote validated memory deltas through IE and governed data access. | 2026-10-12 | 2026-10-13 | 2 | T31 | FS | No | Institutional Memory Store (MEM);Intelligence Engine (IE / Orchestrator);Learning & Performance Engine (W_LEARN) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-13 to 2026-10-14, 2d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: Learning Engine, Memory Store & IE. | Not Started |  |  | 1 | T31 | [7 empty] | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46307.0044 | 1000000000 | 1000000000 | 1000000000 | ;Institutional Memory Store (MEM);Intelligence Engine (IE / Orchestrator);Learning & Performance Engine (W_LEARN); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T33 | Learning & closeout | Validate end-to-end W3C PROV audit lineage, state integrity & logs | Verify entity–activity–agent lineage, signatures, state and execution records. | 2026-10-12 | 2026-10-13 | 2 | T30,T31 | FS | No | W3C PROV Immutable Ledger |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-13 to 2026-10-14, 2d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: W3C PROV Immutable Ledger. | Not Started |  |  | 2 | T30 | T31 | [6 empty] | 36 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46307.0045 | 1000000000 | 1000000000 | 1000000000 | ;W3C PROV Immutable Ledger; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
T34 | Learning & closeout | Perform final project verification against acceptance criteria & close | Verify universal persistence, sandbox coverage and Model A compliance. | 2026-10-14 | 2026-10-14 | 1 | T32,T33 | FS | No | Brand Stakeholder / Portfolio Owner;Intelligence Engine (IE / Orchestrator) |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §1, §2, §4. Original 2026-10-14 to 2026-10-14, 1d; original progress 0% [INFERRED]. [INFERRED] Rescheduled to fit 34d with FS. Original resource/tools: Intelligence Engine & Brand Owner. | Not Started |  |  | 2 | T32 | T33 | [6 empty] | 38 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46309.0046 | 1000000000 | 1000000000 | 1000000000 | ;Brand Stakeholder / Portfolio Owner;Intelligence Engine (IE / Orchestrator); | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
M7 | Learning & closeout | Closed-Loop Telemetry Optimization & Final Project Closeout | Explicit project checkpoint. Mark complete only after linked work is accepted. | 2026-10-14 | 2026-10-14 | 0 | T30,T31,T32,T33,T34 | FF | Yes | Unassigned |  | Not Started | 0% | On track | Source: Project Plan Essentials (2).md §3. Source checkpoint date retained (source labels all dates [INFERRED]). [INFERRED] FF link permits completion-day checkpoint. Owner missing. | Not Started |  |  | 5 | T30 | T31 | T32 | T33 | T34 |  |  |  | 36 | 37 | 38 | 39 | 40 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 46309.0047 | 1000000000 | 1000000000 | ;Unassigned; | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[19 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000000000 | 1000000000 | 1000000000 | 1000000000 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0

## Gantt
Project Gantt | [9 empty] | SEPTEMBER 2026 | [19 empty] | OCTOBER 2026
[10 empty] | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
Gray = not started. Blue = in progress. Green = complete. Red = delayed / overdue. Amber = on hold. ◆ milestone.
Green completion bars show the completed fraction of each day. Schedule conflicts appear in Health.
Task ID | Phase | Task / Activity | Start | End | Days | Progress | Effective Status | Milestone | Health | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14
T01 | Governance & state | Define enterprise objectives, tenant scopes, and budget boundaries | 2026-09-11 | 2026-09-11 | 1 | 0% | Not Started | No | On track | 2026-09-11: 0
T02 | Governance & state | Configure machine-readable policy rules, autonomy tiers, and claim limits | 2026-09-11 | 2026-09-11 | 1 | 0% | Not Started | No | On track | 2026-09-11: 0
T03 | Governance & state | Establish Policy & Authorization Boundary (PAB) evaluation rules | 2026-09-12 | 2026-09-13 | 2 | 0% | Not Started | No | On track | 2026-09-12: 0; 2026-09-13: 0
T04 | Governance & state | Initialize Canonical Task State Machine (CTS) and DAG execution schema | 2026-09-12 | 2026-09-13 | 2 | 0% | Not Started | No | On track | 2026-09-12: 0; 2026-09-13: 0
M1 | Governance & state | Governance, Policy & Canonical State Initialization | 2026-09-14 | 2026-09-14 | 0 | 0% | Not Started | Yes | On track | bar: 2026-09-14
T05 | Data & storage | Provision Central Enterprise Database (CDB) relational tables & vector stores | 2026-09-14 | 2026-09-15 | 2 | 0% | Not Started | No | On track | 2026-09-14: 0; 2026-09-15: 0
T06 | Data & storage | Connect Headless CMS content models and staging layout schemas | 2026-09-14 | 2026-09-15 | 2 | 0% | Not Started | No | On track | 2026-09-14: 0; 2026-09-15: 0
T07 | Data & storage | Instantiate Institutional Memory Store (MEM) for brand heuristics & rules | 2026-09-14 | 2026-09-15 | 2 | 0% | Not Started | No | On track | 2026-09-14: 0; 2026-09-15: 0
T08 | Data & storage | Configure Artifact & Evidence Registry (ART) for UUID/hash deliverables | 2026-09-16 | 2026-09-18 | 3 | 0% | Not Started | No | On track | 2026-09-16: 0; 2026-09-17: 0; 2026-09-18: 0
T09 | Data & storage | Deploy Governed MCP Data Boundary CRUD gateways & connection pools | 2026-09-16 | 2026-09-17 | 2 | 0% | Not Started | No | On track | 2026-09-16: 0; 2026-09-17: 0
T10 | Data & storage | Configure Agentic RAG Controller with tenant isolation & freshness gates | 2026-09-18 | 2026-09-18 | 1 | 0% | Not Started | No | On track | 2026-09-18: 0
M2 | Data & storage | Governed Data Plane & Central Storage Integration (Model A) | 2026-09-19 | 2026-09-19 | 0 | 0% | Not Started | Yes | On track | bar: 2026-09-19
T11 | Sandbox & tools | Deploy agent_sandbox with cgroups, seccomp, and tmpfs isolation | 2026-09-14 | 2026-09-15 | 2 | 0% | Not Started | No | On track | 2026-09-14: 0; 2026-09-15: 0
T12 | Sandbox & tools | Configure sandbox network proxy with strict egress allowlisting (DENY_ALL) | 2026-09-16 | 2026-09-17 | 2 | 0% | Not Started | No | On track | 2026-09-16: 0; 2026-09-17: 0
T13 | Sandbox & tools | Implement sandbox execution audit interception to W3C PROV ledger | 2026-09-18 | 2026-09-19 | 2 | 0% | Not Started | No | On track | 2026-09-18: 0; 2026-09-19: 0
T14 | Sandbox & tools | Instantiate specialist sub-agent micro-tools (S_CODE to S_ATTR) in sandbox | 2026-09-18 | 2026-09-19 | 2 | 0% | Not Started | No | On track | 2026-09-18: 0; 2026-09-19: 0
M3 | Sandbox & tools | Sandbox Isolation & Specialist Sub-Agent Readiness | 2026-09-23 | 2026-09-23 | 0 | 0% | Not Started | Yes | On track | bar: 2026-09-23
T15 | Intelligence & assets | Configure Intelligence Engine context assembly & brand persona layer | 2026-09-19 | 2026-09-19 | 1 | 0% | Not Started | No | On track | 2026-09-19: 0
T16 | Intelligence & assets | Ingest & verify product formulations and compliance dossiers (W_PROD) | 2026-09-20 | 2026-09-21 | 2 | 0% | Not Started | No | On track | 2026-09-20: 0; 2026-09-21: 0
T17 | Intelligence & assets | Ingest & parse customer support tickets and review sentiment (W_VOICE) | 2026-09-20 | 2026-09-21 | 2 | 0% | Not Started | No | On track | 2026-09-20: 0; 2026-09-21: 0
T18 | Intelligence & assets | Scrape competitor ad libraries, pricing, and market positioning (W_COMP) | 2026-09-20 | 2026-09-21 | 2 | 0% | Not Started | No | On track | 2026-09-20: 0; 2026-09-21: 0
T19 | Intelligence & assets | Develop omnichannel marketing roadmaps & budget allocations (W_STRAT) | 2026-09-22 | 2026-09-24 | 3 | 0% | Not Started | No | On track | 2026-09-22: 0; 2026-09-23: 0; 2026-09-24: 0
T20 | Intelligence & assets | Generate creative ad copy variants, hooks, visual briefs & posts (W_CREAT) | 2026-09-25 | 2026-09-27 | 3 | 0% | Not Started | No | On track | 2026-09-25: 0; 2026-09-26: 0; 2026-09-27: 0
T21 | Intelligence & assets | Engineer responsive UI templates, CMS schemas & code diffs (W_DEV) | 2026-09-20 | 2026-09-26 | 7 | 0% | Not Started | No | On track | 2026-09-20: 0; 2026-09-21: 0; 2026-09-22: 0; 2026-09-23: 0; 2026-09-24: 0; 2026-09-25: 0; 2026-09-26: 0
M4 | Intelligence & assets | Domain Intelligence Ingestion & Asset Synthesis Complete | 2026-10-02 | 2026-10-02 | 0 | 0% | Not Started | Yes | On track | bar: 2026-10-02
T22 | Evidence & approval | Consolidate worker evidence envelopes & verify confidence intervals | 2026-09-28 | 2026-09-29 | 2 | 0% | Not Started | No | On track | 2026-09-28: 0; 2026-09-29: 0
T23 | Evidence & approval | Generate structured action previews (spend, code diffs, claims, copy) | 2026-09-30 | 2026-09-30 | 1 | 0% | Not Started | No | On track | 2026-09-30: 0
T24 | Evidence & approval | Execute Human-in-the-Loop (HITL) quality, legal, and deploy sign-off | 2026-10-01 | 2026-10-01 | 1 | 0% | Not Started | No | On track | 2026-10-01: 0
M5 | Evidence & approval | HITL Gateway Clearance & Cryptographic Authorization | 2026-10-06 | 2026-10-06 | 0 | 0% | Not Started | Yes | On track | bar: 2026-10-06
T25 | Launch & telemetry | Initialize Outbound Actuation MCP Boundary with audience tokens | 2026-10-02 | 2026-10-03 | 2 | 0% | Not Started | No | On track | 2026-10-02: 0; 2026-10-03: 0
T26 | Launch & telemetry | Deploy live schemas, catalog updates & layout code to Website & CMS | 2026-10-04 | 2026-10-05 | 2 | 0% | Not Started | No | On track | 2026-10-04: 0; 2026-10-05: 0
T27 | Launch & telemetry | Publish ad campaigns and bid targets to Paid Ad Platforms | 2026-10-04 | 2026-10-05 | 2 | 0% | Not Started | No | On track | 2026-10-04: 0; 2026-10-05: 0
T28 | Launch & telemetry | Publish scheduled social media posts and assets to Social Channels | 2026-10-04 | 2026-10-05 | 2 | 0% | Not Started | No | On track | 2026-10-04: 0; 2026-10-05: 0
T29 | Launch & telemetry | Connect Omnichannel Telemetry Engine webhooks, pixel events & logs | 2026-10-06 | 2026-10-07 | 2 | 0% | Not Started | No | On track | 2026-10-06: 0; 2026-10-07: 0
M6 | Launch & telemetry | Outbound Actuation, Telemetry & Omnichannel Go-Live | 2026-10-10 | 2026-10-10 | 0 | 0% | Not Started | Yes | On track | bar: 2026-10-10
T30 | Learning & closeout | Ingest live store traffic, checkout transactions & conversion logs into CDB | 2026-10-08 | 2026-10-09 | 2 | 0% | Not Started | No | On track | 2026-10-08: 0; 2026-10-09: 0
T31 | Learning & closeout | Calculate multi-touch attribution, creative decay & ROAS (W_LEARN) | 2026-10-10 | 2026-10-11 | 2 | 0% | Not Started | No | On track | 2026-10-10: 0; 2026-10-11: 0
T32 | Learning & closeout | Promote validated memory deltas into Institutional Memory and IE | 2026-10-12 | 2026-10-13 | 2 | 0% | Not Started | No | On track | 2026-10-12: 0; 2026-10-13: 0
T33 | Learning & closeout | Validate end-to-end W3C PROV audit lineage, state integrity & logs | 2026-10-12 | 2026-10-13 | 2 | 0% | Not Started | No | On track | 2026-10-12: 0; 2026-10-13: 0
T34 | Learning & closeout | Perform final project verification against acceptance criteria & close | 2026-10-14 | 2026-10-14 | 1 | 0% | Not Started | No | On track | 2026-10-14: 0
M7 | Learning & closeout | Closed-Loop Telemetry Optimization & Final Project Closeout | 2026-10-14 | 2026-10-14 | 0 | 0% | Not Started | Yes | On track | bar: 2026-10-14

## Dashboard
Project dashboard
Reporting date |  | 2026-09-10 |  | Activities exclude milestones. Progress is duration-weighted.
Total Tasks |  |  | Completed Tasks |  | In-Progress Tasks |  | Not Started Tasks |  | Delayed Tasks | Status | Tasks | Phase | Progress | Milestones | Count | Resource (top 10) | Assigned tasks
34 |  |  | 0 |  | 0 |  | 34 |  | 0 | Not Started | 34 | Governance & state | 0 | Completed | 0 | Specialist Sub-Agents (L4_SUBS) | 8
[10 empty] | In Progress | 0 | Data & storage | 0 | Remaining | 7 | Unassigned | 7
[10 empty] | Completed | 0 | Sandbox & tools | 0 |  |  | Intelligence Engine (IE / Orchestrator) | 5
Overall Progress % |  |  | Total Milestones |  | Completed Milestones |  | Remaining Milestones |  | Project Days Remaining | Delayed | 0 | Intelligence & assets | 0 |  |  | Outbound Actuation MCP Boundary | 4
0% |  |  | 7 |  | 0 |  | 7 |  | 34 | On Hold | 0 | Evidence & approval | 0 |  |  | Sandbox Controller (agent_sandbox) | 3
[12 empty] | Launch & telemetry | 0 |  |  | Brand Stakeholder / Portfolio Owner | 2
[12 empty] | Learning & closeout | 0 |  |  | Central Enterprise Database (CDB) | 2
Schedule exceptions |  | 0 |  | Overdue activities | 0 | On hold |  | 0 | [7 empty] | Headless CMS & Web Store (CMS) | 2
[16 empty] | Institutional Memory Store (MEM) | 2
[16 empty] | W3C PROV Immutable Ledger | 2
Next upcoming activities
Task ID | Task / Activity |  |  |  | Start | End |  | Status | Schedule Health
T01 | Define enterprise objectives, tenant scopes, and budget boundaries |  |  |  | 2026-09-11 | 2026-09-11 |  | Not Started | On track | [8 empty] | 1
T02 | Configure machine-readable policy rules, autonomy tiers, and claim limits |  |  |  | 2026-09-11 | 2026-09-11 |  | Not Started | On track | [8 empty] | 2
T03 | Establish Policy & Authorization Boundary (PAB) evaluation rules |  |  |  | 2026-09-12 | 2026-09-13 |  | Not Started | On track | [8 empty] | 3
T04 | Initialize Canonical Task State Machine (CTS) and DAG execution schema |  |  |  | 2026-09-12 | 2026-09-13 |  | Not Started | On track | [8 empty] | 4
T05 | Provision Central Enterprise Database (CDB) relational tables & vector stores |  |  |  | 2026-09-14 | 2026-09-15 |  | Not Started | On track | [8 empty] | 6
Upcoming milestones
Task ID | Task / Activity |  |  |  | Start | End |  | Status | Schedule Health
M1 | Governance, Policy & Canonical State Initialization |  |  |  | 2026-09-14 | 2026-09-14 |  | Not Started | On track | [8 empty] | 5
M2 | Governed Data Plane & Central Storage Integration (Model A) |  |  |  | 2026-09-19 | 2026-09-19 |  | Not Started | On track | [8 empty] | 12
M3 | Sandbox Isolation & Specialist Sub-Agent Readiness |  |  |  | 2026-09-23 | 2026-09-23 |  | Not Started | On track | [8 empty] | 17
M4 | Domain Intelligence Ingestion & Asset Synthesis Complete |  |  |  | 2026-10-02 | 2026-10-02 |  | Not Started | On track | [8 empty] | 25
M5 | HITL Gateway Clearance & Cryptographic Authorization |  |  |  | 2026-10-06 | 2026-10-06 |  | Not Started | On track | [8 empty] | 29
End date within 7 days
Task ID | Task / Activity |  |  |  | Start | End |  | Status | Schedule Health
T01 | Define enterprise objectives, tenant scopes, and budget boundaries |  |  |  | 2026-09-11 | 2026-09-11 |  | Not Started | On track | [8 empty] | 1
T02 | Configure machine-readable policy rules, autonomy tiers, and claim limits |  |  |  | 2026-09-11 | 2026-09-11 |  | Not Started | On track | [8 empty] | 2
T03 | Establish Policy & Authorization Boundary (PAB) evaluation rules |  |  |  | 2026-09-12 | 2026-09-13 |  | Not Started | On track | [8 empty] | 3
T04 | Initialize Canonical Task State Machine (CTS) and DAG execution schema |  |  |  | 2026-09-12 | 2026-09-13 |  | Not Started | On track | [8 empty] | 4
T05 | Provision Central Enterprise Database (CDB) relational tables & vector stores |  |  |  | 2026-09-14 | 2026-09-15 |  | Not Started | On track | [8 empty] | 6
Delayed or schedule-conflicted
Task ID | Task / Activity |  |  |  | Start | End |  | Status | Schedule Health
0
0
0
0
0
Formulas:
In-Progress Tasks = IF(AD56=0,"",INDEX(Tasks[Start Date],AD56))

## Resources
Resource assignments
Counts include shared roles/tools. Overlap flags concurrent assignments; capacity limits were not supplied.
Resource | Total Assigned Tasks | Completed | In Progress | Remaining | Average Progress | Overlap Days | Notes | Resource token | Unique resource sequence | [9 empty] | 46276 | 46277 | 46278 | 46279 | 46280 | 46281 | 46282 | 46283 | 46284 | 46285 | 46286 | 46287 | 46288 | 46289 | 46290 | 46291 | 46292 | 46293 | 46294 | 46295 | 46296 | 46297 | 46298 | 46299 | 46300 | 46301 | 46302 | 46303 | 46304 | 46305 | 46306 | 46307 | 46308 | 46309
Brand Stakeholder / Portfolio Owner | 2 | 0 | 0 | 2 | 0% | 0 | High strategic responsibility; inputs business goals at kickoff and accepts final delivery at project close. | Brand Stakeholder / Portfolio Owner | 1 | 2.1 | T01 | 0 | 46276 | 46276 | Not Started | No | Brand Stakeholder / Portfolio Owner | High strategic responsibility; inputs business goals at kickoff and accepts final delivery at project close. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Enterprise Policy Engine | 1 | 0 | 0 | 1 | 0% | 0 | Automated policy rule definition; defines risk matrices and compliance envelopes. |  |  | 1.099 | [6 empty] | Enterprise Policy Engine | Automated policy rule definition; defines risk matrices and compliance envelopes. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Policy & Authorization Boundary (PAB) | 1 | 0 | 0 | 1 | 0% | 0 | Core security gate; evaluates caller identity, token validity, and monotonic attenuation per invocation. |  |  | 1.098 | [6 empty] | Policy & Authorization Boundary (PAB) | Core security gate; evaluates caller identity, token validity, and monotonic attenuation per invocation. | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Canonical Task State Machine (CTS) | 1 | 0 | 0 | 1 | 0% | 0 | Central state tracking engine; manages DAG transitions, task holds, checkpoints, and dependency locks. |  |  | 1.097 | [6 empty] | Canonical Task State Machine (CTS) | Central state tracking engine; manages DAG transitions, task holds, checkpoints, and dependency locks. | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unassigned | 7 | 0 | 0 | 7 | 0% | 0 | No capacity or responsibility detail supplied. | Enterprise Policy Engine | 2 | 7.096 | T02 | 0 | 46276 | 46276 | Not Started | No | Central Enterprise Database (CDB) | Primary system of record for operational tables, vector namespaces, and telemetry time-series. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central Enterprise Database (CDB) | 2 | 0 | 0 | 2 | 0% | 0 | Primary system of record for operational tables, vector namespaces, and telemetry time-series. |  |  | 2.095 | [6 empty] | Headless CMS & Web Store (CMS) | Digital asset and page model store; handles staged layout schemas and live storefront content. | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Headless CMS & Web Store (CMS) | 2 | 0 | 0 | 2 | 0% | 0 | Digital asset and page model store; handles staged layout schemas and live storefront content. |  |  | 2.094 | [6 empty] | Institutional Memory Store (MEM) | Long-term knowledge base; stores promoted heuristics, brand voice rules, and model deltas. | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Institutional Memory Store (MEM) | 2 | 0 | 0 | 2 | 0% | 0 | Long-term knowledge base; stores promoted heuristics, brand voice rules, and model deltas. |  |  | 2.093 | [6 empty] | Artifact & Evidence Registry (ART) | Immutable blob storage; stores deliverables, code diffs, and evidence dossiers by UUID/SHA-256. | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Artifact & Evidence Registry (ART) | 1 | 0 | 0 | 1 | 0% | 0 | Immutable blob storage; stores deliverables, code diffs, and evidence dossiers by UUID/SHA-256. | Policy & Authorization Boundary (PAB) | 3 | 1.092 | T03 | 0 | 46277 | 46278 | Not Started | No | Governed MCP Data Boundary | Database gateway; exposes read/write CRUD capability facades under strict schema validation. | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Governed MCP Data Boundary | 1 | 0 | 0 | 1 | 0% | 0 | Database gateway; exposes read/write CRUD capability facades under strict schema validation. |  |  | 1.091 | [6 empty] | Agentic RAG Controller | Sole authorized data broker for Intelligence Engine under Model A; manages hybrid vector search and freshness. | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agentic RAG Controller | 1 | 0 | 0 | 1 | 0% | 0 | Sole authorized data broker for Intelligence Engine under Model A; manages hybrid vector search and freshness. |  |  | 1.09 | [6 empty] | Sandbox Controller (agent_sandbox) | Isolated execution environment; enforces cgroups, seccomp filters, tmpfs shredding, and network proxying. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sandbox Controller (agent_sandbox) | 3 | 0 | 0 | 3 | 0% | 0 | Isolated execution environment; enforces cgroups, seccomp filters, tmpfs shredding, and network proxying. |  |  | 3.089 | [6 empty] | Specialist Sub-Agents (L4_SUBS) | Ephemeral micro-tool workers (S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE, S_ATTR). | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W3C PROV Immutable Ledger | 2 | 0 | 0 | 2 | 0% | 0 | Audit authority; records tamper-evident entity-activity-agent relationships and cryptographic signatures. | Canonical Task State Machine (CTS) | 4 | 2.088 | T04 | 0 | 46277 | 46278 | Not Started | No | Intelligence Engine (IE / Orchestrator) | Primary central planner and MCP host; manages task grants, context assembly, synthesis, and recovery. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Specialist Sub-Agents (L4_SUBS) | 8 | 0 | 0 | 8 | 0% | 7 | Ephemeral micro-tool workers (S_CODE, S_ALLOC, S_COPY, S_VAL, S_SCRAPE, S_PARSE, S_ATTR). |  |  | 8.087 | [6 empty] | Product / Evidence Engine (W_PROD) | Domain worker; ingests formulations, maps clinical evidence, and prepares compliance dossiers. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
Intelligence Engine (IE / Orchestrator) | 5 | 0 | 0 | 5 | 0% | 0 | Primary central planner and MCP host; manages task grants, context assembly, synthesis, and recovery. |  |  | 5.086 | [6 empty] | Customer Voice Engine (W_VOICE) | Domain worker; ingests customer reviews, support tickets, and analyzes sentiment and objection patterns. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Product / Evidence Engine (W_PROD) | 1 | 0 | 0 | 1 | 0% | 0 | Domain worker; ingests formulations, maps clinical evidence, and prepares compliance dossiers. |  |  | 1.085 | [6 empty] | Competitor Intel Engine (W_COMP) | Domain worker; monitors competitor pricing, ad copy trends, and positioning shifts. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer Voice Engine (W_VOICE) | 1 | 0 | 0 | 1 | 0% | 0 | Domain worker; ingests customer reviews, support tickets, and analyzes sentiment and objection patterns. | Unassigned | 5 | 1.084 | M1 | 0 | 46279 | 46279 | Not Started | Yes | Strategy Engine (W_STRAT) | Domain worker; formulates omnichannel roadmaps, funnel structures, and budget allocation proposals. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Competitor Intel Engine (W_COMP) | 1 | 0 | 0 | 1 | 0% | 0 | Domain worker; monitors competitor pricing, ad copy trends, and positioning shifts. |  |  | 1.083 | [6 empty] | Creative & Content Engine (W_CREAT) | Domain worker; drafts multi-channel copy, creative hooks, visual briefs, and social media schedules. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strategy Engine (W_STRAT) | 1 | 0 | 0 | 1 | 0% | 0 | Domain worker; formulates omnichannel roadmaps, funnel structures, and budget allocation proposals. |  |  | 1.082 | [6 empty] | Development Engine (W_DEV) | Domain worker; engineers responsive UI components, CMS schemas, layout templates, and code diffs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Creative & Content Engine (W_CREAT) | 1 | 0 | 0 | 1 | 0% | 0 | Domain worker; drafts multi-channel copy, creative hooks, visual briefs, and social media schedules. |  |  | 1.081 | [6 empty] | Human-in-the-Loop (HITL) Gate | Mandatory human sign-off; reviews action previews for spend, legal compliance, and code deployment. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Engine (W_DEV) | 1 | 0 | 0 | 1 | 0% | 0 | Domain worker; engineers responsive UI components, CMS schemas, layout templates, and code diffs. | Central Enterprise Database (CDB) | 6 | 1.08 | T05 | 0 | 46279 | 46280 | Not Started | No | Outbound Actuation MCP Boundary | Security egress perimeter; validates audience tokens and dispatches signed API calls to external surfaces. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Human-in-the-Loop (HITL) Gate | 1 | 0 | 0 | 1 | 0% | 0 | Mandatory human sign-off; reviews action previews for spend, legal compliance, and code deployment. |  |  | 1.079 | [6 empty] | Live Website & Headless CMS Surface | External production runtime; hosts live storefront, product catalog, and user-facing web applications. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Outbound Actuation MCP Boundary | 4 | 0 | 0 | 4 | 0% | 2 | Security egress perimeter; validates audience tokens and dispatches signed API calls to external surfaces. |  |  | 4.078 | [6 empty] | Paid Ad Platforms (Meta, Google, TikTok) | External media platforms; receives campaign payloads, audience targeting, and spend allocations. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Live Website & Headless CMS Surface | 1 | 0 | 0 | 1 | 0% | 0 | External production runtime; hosts live storefront, product catalog, and user-facing web applications. |  |  | 1.077 | [6 empty] | Social Channels (Instagram, X, YouTube) | External content channels; receives scheduled social posts, copy packages, and media assets. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paid Ad Platforms (Meta, Google, TikTok) | 1 | 0 | 0 | 1 | 0% | 0 | External media platforms; receives campaign payloads, audience targeting, and spend allocations. | Headless CMS & Web Store (CMS) | 7 | 1.076 | T06 | 0 | 46279 | 46280 | Not Started | No | Omnichannel Telemetry Engine | Real-time event ingestor; aggregates conversion webhooks, pixel events, and server logs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Social Channels (Instagram, X, YouTube) | 1 | 0 | 0 | 1 | 0% | 0 | External content channels; receives scheduled social posts, copy packages, and media assets. |  |  | 1.075 | [6 empty] | Learning & Performance Engine (W_LEARN) | Domain worker; calculates attribution curves, creative fatigue, ROAS optimization, and memory deltas. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Omnichannel Telemetry Engine | 2 | 0 | 0 | 2 | 0% | 0 | Real-time event ingestor; aggregates conversion webhooks, pixel events, and server logs. |  |  | 2.074 | [6 empty] | W3C PROV Immutable Ledger | Audit authority; records tamper-evident entity-activity-agent relationships and cryptographic signatures. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Learning & Performance Engine (W_LEARN) | 2 | 0 | 0 | 2 | 0% | 0 | Domain worker; calculates attribution curves, creative fatigue, ROAS optimization, and memory deltas. |  |  | 2.073 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
[8 empty] | Institutional Memory Store (MEM) | 8 | 0 | T07 | 0 | 46279 | 46280 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Artifact & Evidence Registry (ART) | 9 | 0 | T08 | 0 | 46281 | 46283 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Governed MCP Data Boundary | 10 | 0 | T09 | 0 | 46281 | 46282 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Agentic RAG Controller | 11 | 0 | T10 | 0 | 46283 | 46283 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Unassigned |  | 0 | M2 | 0 | 46284 | 46284 | Not Started | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Sandbox Controller (agent_sandbox) | 12 | 0 | T11 | 0 | 46279 | 46280 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Sandbox Controller (agent_sandbox) |  | 0 | T12 | 0 | 46281 | 46282 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Sandbox Controller (agent_sandbox) |  | 0 | T13 | 0 | 46283 | 46284 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | W3C PROV Immutable Ledger | 13 | 0 | T13 | 0 | 46283 | 46284 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Specialist Sub-Agents (L4_SUBS) | 14 | 0 | T14 | 0 | 46283 | 46284 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Unassigned |  | 0 | M3 | 0 | 46288 | 46288 | Not Started | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Intelligence Engine (IE / Orchestrator) | 15 | 0 | T15 | 0 | 46284 | 46284 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Specialist Sub-Agents (L4_SUBS) |  | 0 | T16 | 0 | 46285 | 46286 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Product / Evidence Engine (W_PROD) | 16 | 0 | T16 | 0 | 46285 | 46286 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Specialist Sub-Agents (L4_SUBS) |  | 0 | T17 | 0 | 46285 | 46286 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Customer Voice Engine (W_VOICE) | 17 | 0 | T17 | 0 | 46285 | 46286 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Specialist Sub-Agents (L4_SUBS) |  | 0 | T18 | 0 | 46285 | 46286 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Competitor Intel Engine (W_COMP) | 18 | 0 | T18 | 0 | 46285 | 46286 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Specialist Sub-Agents (L4_SUBS) |  | 0 | T19 | 0 | 46287 | 46289 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Strategy Engine (W_STRAT) | 19 | 0 | T19 | 0 | 46287 | 46289 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Specialist Sub-Agents (L4_SUBS) |  | 0 | T20 | 0 | 46290 | 46292 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Creative & Content Engine (W_CREAT) | 20 | 0 | T20 | 0 | 46290 | 46292 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Specialist Sub-Agents (L4_SUBS) |  | 0 | T21 | 0 | 46285 | 46291 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Development Engine (W_DEV) | 21 | 0 | T21 | 0 | 46285 | 46291 | Not Started | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Unassigned |  | 0 | M4 | 0 | 46297 | 46297 | Not Started | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Intelligence Engine (IE / Orchestrator) |  |  | T22 | 0 | 46293 | 46294 | Not Started | No
[8 empty] | Intelligence Engine (IE / Orchestrator) |  |  | T23 | 0 | 46295 | 46295 | Not Started | No
[8 empty] | Human-in-the-Loop (HITL) Gate | 22 |  | T24 | 0 | 46296 | 46296 | Not Started | No
[8 empty] | Unassigned |  |  | M5 | 0 | 46301 | 46301 | Not Started | Yes
[8 empty] | Outbound Actuation MCP Boundary | 23 |  | T25 | 0 | 46297 | 46298 | Not Started | No
[8 empty] | Headless CMS & Web Store (CMS) |  |  | T26 | 0 | 46299 | 46300 | Not Started | No
[8 empty] | Outbound Actuation MCP Boundary |  |  | T26 | 0 | 46299 | 46300 | Not Started | No
[8 empty] | Live Website & Headless CMS Surface | 24 |  | T26 | 0 | 46299 | 46300 | Not Started | No
[8 empty] | Outbound Actuation MCP Boundary |  |  | T27 | 0 | 46299 | 46300 | Not Started | No
[8 empty] | Paid Ad Platforms (Meta, Google, TikTok) | 25 |  | T27 | 0 | 46299 | 46300 | Not Started | No
[8 empty] | Outbound Actuation MCP Boundary |  |  | T28 | 0 | 46299 | 46300 | Not Started | No
[8 empty] | Social Channels (Instagram, X, YouTube) | 26 |  | T28 | 0 | 46299 | 46300 | Not Started | No
[8 empty] | Omnichannel Telemetry Engine | 27 |  | T29 | 0 | 46301 | 46302 | Not Started | No
[8 empty] | Unassigned |  |  | M6 | 0 | 46305 | 46305 | Not Started | Yes
[8 empty] | Central Enterprise Database (CDB) |  |  | T30 | 0 | 46303 | 46304 | Not Started | No
[8 empty] | Omnichannel Telemetry Engine |  |  | T30 | 0 | 46303 | 46304 | Not Started | No
[8 empty] | Specialist Sub-Agents (L4_SUBS) |  |  | T31 | 0 | 46305 | 46306 | Not Started | No
[8 empty] | Learning & Performance Engine (W_LEARN) | 28 |  | T31 | 0 | 46305 | 46306 | Not Started | No
[8 empty] | Institutional Memory Store (MEM) |  |  | T32 | 0 | 46307 | 46308 | Not Started | No
[8 empty] | Intelligence Engine (IE / Orchestrator) |  |  | T32 | 0 | 46307 | 46308 | Not Started | No
[8 empty] | Learning & Performance Engine (W_LEARN) |  |  | T32 | 0 | 46307 | 46308 | Not Started | No
[8 empty] | W3C PROV Immutable Ledger |  |  | T33 | 0 | 46307 | 46308 | Not Started | No
[8 empty] | Brand Stakeholder / Portfolio Owner |  |  | T34 | 0 | 46309 | 46309 | Not Started | No
[8 empty] | Intelligence Engine (IE / Orchestrator) |  |  | T34 | 0 | 46309 | 46309 | Not Started | No
[8 empty] | Unassigned |  |  | M7 | 0 | 46309 | 46309 | Not Started | Yes

## Assumptions & Gaps
Assumptions & gaps
Label | Source field / item | Issue | Resolution used | User action needed
[CONFLICT] | Plan §1, §2.2. Dates vs FS dependencies | Original durations require 48 calendar days under inclusive dates and next-day FS, exceeding the 34-day window. Several source tasks start on predecessor finish dates. | Provisional compressed schedule. Original dates/durations preserved per task. FS requires next-day start after an activity; zero-day milestone FS permits its date. | Validate reduced durations with delivery owners before committing.
[INFERRED] | All activity dates / reduced durations | Plan §6 says source dates were inferred from architecture. No effort estimates, staffing or capacity evidence supplied. | Schedule from 11 Sep using dependency order. Reduce a longest relative-duration task on the critical path by one day until the span is 34 days. No capacity assumptions. | Approve or revise estimates. A valid date graph does not prove delivery feasibility.
[CONFLICT] | Plan §1 and §5 progress | Source completion values are explicitly [INFERRED], not evidence of actual execution. | All activities and milestones initialized to 0% as requested. Original source values remain in task notes. | Enter actual progress only after work is completed.
[CONFLICT] | T18 predecessor set, plan §1 / §2.1 vs §2.2 | Task table says T12,T14,T15; dependency details say T10,T14,T15. | Retained union T10,T12,T14,T15, all FS. | Confirm intended prerequisites.
[INFERRED] | T08 and T12 dependency type | Dependencies exist but type is absent from detailed dependency table. | Defaulted to FS. | Confirm type if overlap is allowed.
[INFERRED] | M1–M7 dependency type | Explicit checkpoint links exist but dependency types do not. | FF links to all listed tasks. Original milestone dates retained. Milestone Duration is zero. | Mark each milestone complete only after acceptance.
[MISSING] | Priority and named human owners | No High/Medium/Low priorities or named individuals supplied. Sources mostly assign components and tools. | Priorities left blank. Canonical roles/tools from plan §4 retained; milestone owners Unassigned. | Assign accountable people and task priorities.
[CONFLICT] | Architecture §1, §3 vs Model A §4; matching HTML diagram | CDB directly feeds W_LEARN in the graph/table, while Model A forbids direct worker database access. | T31 description/instructions require IE-mediated access. Diagram contradiction retained as an unresolved design issue. | Confirm the permitted telemetry retrieval route.
[CONFLICT] | Architecture §4 sketch vs §1 / Model A | Plaintext sketch suggests an IE-to-database universal persistence bridge outside RAG/MCP. | Planning uses the stated exclusive IE → RAG → governed data access model. | Resolve whether the sketch is shorthand or a separate authorized path.
[CONFLICT] | Plan §4 channel lists vs architecture and HTML | Architecture adds LinkedIn paid ads and TikTok social to shorter plan resource lists. | Task scope notes retain all channels as a confirmation item; no invented channel-specific tasks. | Confirm channels included in T27 / T28.
[MISSING] | T25 credentials and production access | No platform client secrets, OAuth accounts or deployment endpoints supplied. | Retained as execution prerequisite in T25. No credentials placed in workbook. | Provide secure access before actuation setup.
[MISSING] | T01 / T19 budgets and capacity | Budget caps and capacity are conceptual; numeric amounts and staffing are absent. | No budget or capacity values invented. Resources show overlap days without asserting overload. | Supply budget caps and resource availability.
[INFERRED] | Phase labels | Plan associates tasks with M1–M7 but lacks short phase names. | Seven workstreams named from milestone scope. | Rename Phase cells if needed.
[INFERRED] | Resource normalization | Plan §1 uses shortened/combined tool labels; §4 lists shared canonical assignments. | Use semicolon-separated §4 roles so shared resources aggregate. §1 tools preserved in Notes. | Keep resource spelling consistent.
[INFERRED] | T01 duration | 2 calendar days in source. | 1 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T02 duration | 2 calendar days in source. | 1 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T03 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T04 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T05 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T06 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T07 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T09 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T10 duration | 2 calendar days in source. | 1 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T11 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T14 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T15 duration | 2 calendar days in source. | 1 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T16 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T17 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T18 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T19 duration | 4 calendar days in source. | 3 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T20 duration | 4 calendar days in source. | 3 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T22 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T23 duration | 2 calendar days in source. | 1 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T24 duration | 2 calendar days in source. | 1 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T26 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T27 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T28 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.
[INFERRED] | T31 duration | 3 calendar days in source. | 2 calendar days in provisional schedule. | Confirm estimate and delivery capacity.

## Instructions
Instructions
Project start |  | Project end |  | Reporting date
| 2026-09-11 |  | 2026-10-14 |  | 2026-09-10
Edit tasks | Use blue input cells in Project Tracker. Duration and Schedule Health are calculated. Blank rows are excluded from every metric until a Task ID is entered.
Change dates | Enter real Excel dates. Calendar-day durations include both Start and End. Dates are editable; successors are flagged when dates violate dependencies, not silently moved.
Update progress | Type 25% or 0.25, not 25. Valid range is 0%–100%. Progress starts at 0%. Task progress is independent of milestone acceptance.
Change status | Status starts as a formula from progress. Use the dropdown to set On Hold or Delayed; these manual exceptions persist. Gantt/dashboard otherwise use progress. To return to automatic status, copy a normal Status formula into that row. A stale manual normal status is flagged.
Assign resources | Use consistent role/person names separated by semicolons, without spaces beside delimiters. Up to four resources per task and 100 distinct names. New names appear automatically on Resources. No assignment capacity is assumed.
Dependencies | Use up to eight comma-separated exact Task IDs. One Dependency Type applies to every predecessor on a row. FS: start after predecessor finish; SS: start on/after predecessor start; FF: finish on/after predecessor finish; SF: finish on/after predecessor start. No lag field is provided.
Add a task safely | Use the next blank row in the 100-row Tasks table. Enter a unique ID, Phase, name, dates, Milestone Yes/No, resources and 0% progress. Formulas, validations, Gantt and dashboard are already prepared through tracker row 106. Do not insert rows or exceed 100 records without extending all helper/view ranges.
Milestone markers | Set Milestone to Yes and enter the same Start and End date. Duration becomes 0 and the Gantt displays ◆. The progress field records acceptance; 100% completes the dashboard milestone count.
Gantt updates | Every cell corresponds to one calendar day from 11 Sep to 14 Oct. Base fill shows status; green data bars show the completed fraction within each day. At 0% there is no completed portion. Weekends are gray outside bars.
Dashboard indicators | Total Tasks and status cards count non-milestone activities. Overall Progress is duration-weighted across activities. Milestone cards use Progress %. Delayed counts manual Delayed statuses; Overdue is shown separately. Exceptions include invalid dates, IDs and dependency conflicts.
Reporting date | F5 defaults to TODAY so overdue and upcoming lists refresh on recalculation. Replace it with a reporting date to review a fixed point in time; restore =TODAY() for live tracking. This is the only volatile formula.
Resource overlap | Overlap Days counts calendar dates with more than one non-milestone assignment to the same resource. Shared automated tools can run concurrently; an overlap is not proof of overload. Counts include each assigned role, so totals can exceed task count.
Schedule warnings | Fix Missing ID, Cycle or blocked by cycle, Timing conflict, End before start and Outside Window warnings in the tracker. Cycle detection performs 100 topological passes and flags both cycle members and downstream blocked work.
Formula protection | Calculated cells and output sheets are protected without a password. Inputs remain editable. Use Review → Unprotect Sheet for structural maintenance. Keep the 100 prepared rows to avoid breaking views and validation.
Source map | P = Project Plan Essentials-Governed Multi-Brand Agentic System(2).md. Architecture = Final-Level Full Architecture(2).md. Diagram = flowchart.drawio(2).html. Read all three completely; HTML embedded Mermaid matches the architecture graph after escape normalization.
Execution boundaries | This workbook plans work only. T24 retains explicit human approval before T25–T28. T31 retrieval follows Model A through IE and RAG; source bypass arrows need resolution.
Provisional estimates | Original dates, durations and inferred progress remain in task Notes. Reduced durations are listed in Assumptions & Gaps. No staffing evidence supports the compression; confirm estimates before committing the 34-day plan.